## Schedule
Category | Task | Description | Start Day | Duration (days) | Assigned To (User) | Assigned To (Supplier) | Predecessors | Predecessor Relations
Deposit | New Task |  | 0 | 1
Foundations | Site Scrape |  | 1 | 1
Foundations | Surveyor Set Out |  | 2 | 1 |  |  | Site Scrape | 0 FS
Foundations | Bulk Earthworks |  | 3 | 1 |  |  | Surveyor Set Out | 0 FS
Foundations | Reo Delivery |  | 4 | 1 |  |  | Bulk Earthworks | 0 FS
Foundations | Dig Footings |  | 5 | 1 |  |  | Reo Delivery | 0 FS
Foundations | Reinforce footings |  | 6 | 1 |  |  | Dig Footings | 0 FS
Foundations | Footing Inspection |  | 7 | 1 |  |  | Reinforce footings | 0 FS
Foundations | Pour Footings |  | 8 | 1 |  |  | Footing Inspection | 0 FS
Foundations | Brick Delivery |  | 9 | 1 |  |  | Pour Footings | 0 FS
Foundations | Brick / Block Base |  | 10 | 1 |  |  | Brick Delivery | 0 FS
Foundations | Core Fill |  | 11 | 1 |  |  | Brick / Block Base | 0 FS
Foundations | Waterproof Foundations |  | 12 | 1 |  |  | Core Fill | 0 FS
Foundations | Structural wall drainage |  | 13 | 1 |  |  | Waterproof Foundations | 0 FS
Foundations | Slab Earthworks |  | 14 | 1 |  |  | Structural wall drainage | 0 FS
Foundations | Install formwork |  | 15 | 1 |  |  | Slab Earthworks | 0 FS
Foundations | Internal Drainage |  | 16 | 1 |  |  | Install formwork | 0 FS
Foundations | Drainage inspection |  | 17 | 1 |  |  | Internal Drainage | 0 FS
Foundations | Install Slab Reinforcement |  | 18 | 1 |  |  | Drainage inspection | 0 FS
Foundations | Slab Inspection |  | 19 | 1 |  |  | Install Slab Reinforcement | 0 FS
Foundations | Slab Pour |  | 20 | 1 |  |  | Slab Inspection | 0 FS
Foundations | Invoice Foundation stage |  | 21 | 1 |  |  | Slab Pour | 0 FS
Frames | Termite Barrier |  | 22 | 1 |  |  | Invoice Foundation stage | 0 FS
Frames | Subfloor Delivery |  | 23 | 1 |  |  | Termite Barrier | 0 FS
Frames | Sub Floor Framing |  | 24 | 1 |  |  | Subfloor Delivery | 0 FS
Frames | Sub Floor insulation |  | 25 | 1 |  |  | Sub Floor Framing | 0 FS
Frames | Wall Frame delivery |  | 26 | 1 |  |  | Sub Floor insulation | 0 FS
Frames | Frame Walls |  | 27 | 1 |  |  | Wall Frame delivery | 0 FS
Frames | Truss Delivery |  | 28 | 1 |  |  | Frame Walls | 0 FS
Frames | Install Trusses / Roof Framing |  | 29 | 1 |  |  | Truss Delivery | 0 FS
Frames | Frame Inspection |  | 30 | 1 |  |  | Install Trusses / Roof Framing | 0 FS
Frames | Invoice Frame stage |  | 31 | 1 |  |  | Frame Inspection | 0 FS
WRB | WRB Delivery or pick-up |  | 32 | 1 |  |  | Invoice Frame stage | 0 FS
WRB | Cavity Batten Delivery |  | 33 | 1 |  |  | WRB Delivery or pick-up | 0 FS
WRB | Install Roof Wrap |  | 34 | 1 |  |  | Cavity Batten Delivery | 0 FS
WRB | Install wall wrap |  | 35 | 1 |  |  | Install Roof Wrap | 0 FS
WRB | Window Delivery |  | 36 | 1 |  |  | Install wall wrap | 0 FS
WRB | Window Install |  | 37 | 1 |  |  | Window Delivery | 0 FS
WRB | Electrical Rough in |  | 38 | 1 |  |  | Window Install | 0 FS
WRB | Plumbing Rough in |  | 39 | 1 |  |  | Electrical Rough in | 0 FS
WRB | Plumbing Inwall delivery |  | 40 | 1 |  |  | Plumbing Rough in | 0 FS
WRB | Solar Rough in |  | 41 | 1 |  |  | Plumbing Inwall delivery | 0 FS
WRB | Blower Door Test |  | 42 | 1 |  |  | Solar Rough in | 0 FS
WRB | WRB Inspection |  | 43 | 1 |  |  | Blower Door Test | 0 FS
WRB | Invoice WRB Stage |  | 44 | 1 |  |  | WRB Inspection | 0 FS
Lock-Up | Roof Delivery |  | 45 | 1 |  |  | Invoice WRB Stage | 0 FS
Lock-Up | Install Facia & Gutter |  | 46 | 1 |  |  | Roof Delivery | 0 FS
Lock-Up | Install roof Rail |  | 47 | 1 |  |  | Install Facia & Gutter | 0 FS
Lock-Up | Install Roof |  | 48 | 1 |  |  | Install roof Rail | 0 FS
Lock-Up | Cladding Delivery |  | 49 | 1 |  |  | Install Roof | 0 FS
Lock-Up | install Ventilation details |  | 50 | 1 |  |  | Cladding Delivery | 0 FS
Lock-Up | Install Cladding |  | 51 | 1 |  |  | install Ventilation details | 0 FS
Lock-Up | Install Eaves |  | 52 | 1 |  |  | Install Cladding | 0 FS
Lock-Up | Invoice Lock-up Stage |  | 53 | 1 |  |  | Install Eaves | 0 FS
Lock-Up | Frame Decks |  | 54 | 1 |  |  | Invoice Lock-up Stage | 0 FS
Lock-Up | External Drainage |  | 55 | 1 |  |  | Frame Decks | 0 FS
Lock-Up | Invoice Lock-up |  | 56 | 1 |  |  | External Drainage | 0 FS
Internal Linings | Pre sheet |  | 57 | 1 |  |  | Invoice Lock-up | 0 FS
Internal Linings | Joinery On-site Measure |  | 58 | 1 |  |  | Pre sheet | 0 FS
Internal Linings | Insulation Delivery |  | 59 | 1 |  |  | Joinery On-site Measure | 0 FS
Internal Linings | Install Insulation |  | 60 | 1 |  |  | Insulation Delivery | 0 FS
Internal Linings | Insulation Inspection |  | 61 | 1 |  |  | Install Insulation | 0 FS
Internal Linings | Plasterboard Install |  | 62 | 1 |  |  | Insulation Inspection | 0 FS
Internal Linings | Electrical cut out |  | 63 | 1 |  |  | Plasterboard Install | 0 FS
Internal Linings | HVAC Cut Out |  | 64 | 1 |  |  | Electrical cut out | 0 FS
Internal Linings | Waterproof Base |  | 65 | 1 |  |  | HVAC Cut Out | 0 FS
Internal Linings | Waterproof inspection |  | 66 | 1 |  |  | Waterproof Base | 0 FS
Internal Linings | External Painting |  | 67 | 1 |  |  | Waterproof inspection | 0 FS
Internal Linings | Tile Screed |  | 68 | 1 |  |  | External Painting | 0 FS
Internal Linings | Waterproof Screed |  | 69 | 1 |  |  | Tile Screed | 0 FS
Internal Linings | Waterproof inspection |  | 70 | 1 |  |  | Waterproof Screed | 0 FS
Internal Linings | Fix-out material delivery |  | 71 | 1 |  |  | Waterproof inspection | 0 FS
Internal Linings | Install fix-out |  | 72 | 1 |  |  | Fix-out material delivery | 0 FS
Internal Linings | Tile Delivery |  | 73 | 1 |  |  | Install fix-out | 0 FS
Internal Linings | Install wet area Tiling |  | 74 | 1 |  |  | Tile Delivery | 0 FS
Internal Linings | Joinery Install |  | 75 | 1 |  |  | Install wet area Tiling | 0 FS
Internal Linings | Internal Linings Invoice |  | 76 | 1 |  |  | Joinery Install | 0 FS
Fixtures & Finishes | Internal Painting |  | 77 | 1 |  |  | Internal Linings Invoice | 0 FS
Fixtures & Finishes | Hard Floor Coverings |  | 78 | 1 |  |  | Internal Painting | 0 FS
Fixtures & Finishes | Appliances & Fixtures Delivery |  | 79 | 1 |  |  | Hard Floor Coverings | 0 FS
Fixtures & Finishes | Carpentry Fit-off |  | 80 | 1 |  |  | Appliances & Fixtures Delivery | 0 FS
Fixtures & Finishes | Plumbing Fit Off |  | 81 | 1 |  |  | Carpentry Fit-off | 0 FS
Fixtures & Finishes | Electrical Fitoff |  | 82 | 1 |  |  | Plumbing Fit Off | 0 FS
Fixtures & Finishes | Shower screen install |  | 83 | 1 |  |  | Electrical Fitoff | 0 FS
Fixtures & Finishes | Invoice Fixtures & Finishes |  | 84 | 1 |  |  | Shower screen install | 0 FS
Finals | Decking Delivery |  | 85 | 1 |  |  | Invoice Fixtures & Finishes | 0 FS
Finals | Install Decking |  | 86 | 1 |  |  | Decking Delivery | 0 FS
Finals | Balustrade delivery |  | 87 | 1 |  |  | Install Decking | 0 FS
Finals | Install Balustrade |  | 88 | 1 |  |  | Balustrade delivery | 0 FS
Finals | Carpet Install |  | 89 | 1 |  |  | Install Balustrade | 0 FS
Finals | Fly screen install |  | 90 | 1 |  |  | Carpet Install | 0 FS
Finals | Silicone & Caulking |  | 91 | 1 |  |  | Fly screen install | 0 FS
Finals | Defect Walkthrough |  | 92 | 1 |  |  | Silicone & Caulking | 0 FS
Finals | Window Cleaning |  | 93 | 1 |  |  | Defect Walkthrough | 0 FS
Finals | House Cleaning |  | 94 | 1 |  |  | Window Cleaning | 0 FS

## Tasks
Category | Task | Start Day | Duration | Assigned To (User) | Assigned To (Supplier) | Subtask | Subtask Description | Subtask Due Date | Subtask Due Date Number of Days | Subtask Checklist Template | Subtask Checklist Template Group
Deposit | New Task | 0 | 1
Foundations | Site Scrape | 1 | 1
Foundations | Surveyor Set Out | 2 | 1
Foundations | Bulk Earthworks | 3 | 1
Foundations | Reo Delivery | 4 | 1
Foundations | Dig Footings | 5 | 1
Foundations | Reinforce footings | 6 | 1
Foundations | Footing Inspection | 7 | 1
Foundations | Pour Footings | 8 | 1
Foundations | Brick Delivery | 9 | 1
Foundations | Brick / Block Base | 10 | 1
Foundations | Core Fill | 11 | 1
Foundations | Waterproof Foundations | 12 | 1
Foundations | Structural wall drainage | 13 | 1
Foundations | Slab Earthworks | 14 | 1
Foundations | Install formwork | 15 | 1
Foundations | Internal Drainage | 16 | 1
Foundations | Drainage inspection | 17 | 1
Foundations | Install Slab Reinforcement | 18 | 1
Foundations | Slab Inspection | 19 | 1
Foundations | Slab Pour | 20 | 1
Foundations | Invoice Foundation stage | 21 | 1
Frames | Termite Barrier | 22 | 1
Frames | Subfloor Delivery | 23 | 1
Frames | Sub Floor Framing | 24 | 1
Frames | Sub Floor insulation | 25 | 1
Frames | Wall Frame delivery | 26 | 1
Frames | Frame Walls | 27 | 1
Frames | Truss Delivery | 28 | 1
Frames | Install Trusses / Roof Framing | 29 | 1
Frames | Frame Inspection | 30 | 1
Frames | Invoice Frame stage | 31 | 1
WRB | WRB Delivery or pick-up | 32 | 1
WRB | Cavity Batten Delivery | 33 | 1
WRB | Install Roof Wrap | 34 | 1
WRB | Install wall wrap | 35 | 1
WRB | Window Delivery | 36 | 1
WRB | Window Install | 37 | 1
WRB | Electrical Rough in | 38 | 1
WRB | Plumbing Rough in | 39 | 1
WRB | Plumbing Inwall delivery | 40 | 1
WRB | Solar Rough in | 41 | 1
WRB | Blower Door Test | 42 | 1
WRB | WRB Inspection | 43 | 1
WRB | Invoice WRB Stage | 44 | 1
Lock-Up | Roof Delivery | 45 | 1
Lock-Up | Install Facia & Gutter | 46 | 1
Lock-Up | Install roof Rail | 47 | 1
Lock-Up | Install Roof | 48 | 1
Lock-Up | Cladding Delivery | 49 | 1
Lock-Up | install Ventilation details | 50 | 1
Lock-Up | Install Cladding | 51 | 1
Lock-Up | Install Eaves | 52 | 1
Lock-Up | Invoice Lock-up Stage | 53 | 1
Lock-Up | Frame Decks | 54 | 1
Lock-Up | External Drainage | 55 | 1
Lock-Up | Invoice Lock-up | 56 | 1
Internal Linings | Pre sheet | 57 | 1
Internal Linings | Joinery On-site Measure | 58 | 1
Internal Linings | Insulation Delivery | 59 | 1
Internal Linings | Install Insulation | 60 | 1
Internal Linings | Insulation Inspection | 61 | 1
Internal Linings | Plasterboard Install | 62 | 1
Internal Linings | Electrical cut out | 63 | 1
Internal Linings | HVAC Cut Out | 64 | 1
Internal Linings | Waterproof Base | 65 | 1
Internal Linings | Waterproof inspection | 66 | 1
Internal Linings | External Painting | 67 | 1
Internal Linings | Tile Screed | 68 | 1
Internal Linings | Waterproof Screed | 69 | 1
Internal Linings | Waterproof inspection | 70 | 1
Internal Linings | Fix-out material delivery | 71 | 1
Internal Linings | Install fix-out | 72 | 1
Internal Linings | Tile Delivery | 73 | 1
Internal Linings | Install wet area Tiling | 74 | 1
Internal Linings | Joinery Install | 75 | 1
Internal Linings | Internal Linings Invoice | 76 | 1
Fixtures & Finishes | Internal Painting | 77 | 1
Fixtures & Finishes | Hard Floor Coverings | 78 | 1
Fixtures & Finishes | Appliances & Fixtures Delivery | 79 | 1
Fixtures & Finishes | Carpentry Fit-off | 80 | 1
Fixtures & Finishes | Plumbing Fit Off | 81 | 1
Fixtures & Finishes | Electrical Fitoff | 82 | 1
Fixtures & Finishes | Shower screen install | 83 | 1
Fixtures & Finishes | Invoice Fixtures & Finishes | 84 | 1
Finals | Decking Delivery | 85 | 1
Finals | Install Decking | 86 | 1
Finals | Balustrade delivery | 87 | 1
Finals | Install Balustrade | 88 | 1
Finals | Carpet Install | 89 | 1
Finals | Fly screen install | 90 | 1
Finals | Silicone & Caulking | 91 | 1
Finals | Defect Walkthrough | 92 | 1
Finals | Window Cleaning | 93 | 1
Finals | House Cleaning | 94 | 1