## To-Dos
Name | Parent | Description | Status | Priority | Assignees | Due date | Labels | Attachments
JC02 - CONTRACTS PROCESS |  | https://docs.google.com/document/d/16CZV-kR6TarniWlP5T4uK-tYFXSvT4eFWI8X3FlSLB8/edit?tab=t.cwiflssg2iyi | Not Started | Low |  |  | Job Stage
01. Receive written approval from the client | JC02 - CONTRACTS PROCESS |  | Not Started | Low | Riza Urmeneta |  | Job Stage
02. Saves files to folder | JC02 - CONTRACTS PROCESS |  | Not Started | Low | Riza Urmeneta |  | Job Stage
03. Create JOB SHEET Spreadsheet | JC02 - CONTRACTS PROCESS |  | Not Started | Low | Riza Urmeneta |  | Job Stage
04. Send Client Contract Info Sheet form | JC02 - CONTRACTS PROCESS |  | Not Started | Low | Riza Urmeneta |  | Job Stage
05. Create Progress Payments in Job Sheet | JC02 - CONTRACTS PROCESS |  | Not Started | Low | Jed Smith |  | Job Stage
06. Determine HBCF cost for contract | JC02 - CONTRACTS PROCESS |  | Not Started | Low | Riza Urmeneta |  | Job Stage
07. Create Job Number | JC02 - CONTRACTS PROCESS |  | Not Started | Low | Riza Urmeneta |  | Job Stage
08. Create & Customise Contract Docments | JC02 - CONTRACTS PROCESS |  | Not Started | Low | Riza Urmeneta |  | Job Stage
09. Check draft for mistakes | JC02 - CONTRACTS PROCESS |  | Not Started | Low | Jed Smith |  | Job Stage
10. Finalise Contract Documents | JC02 - CONTRACTS PROCESS |  | Not Started | Low | Riza Urmeneta |  | Job Stage
11. Enter into Docusign | JC02 - CONTRACTS PROCESS |  | Not Started | Low | Riza Urmeneta |  | Job Stage
12. Create initial schedule | JC02 - CONTRACTS PROCESS |  | Not Started | Low | Jed Smith |  | Job Stage
13. Finalise signing | JC02 - CONTRACTS PROCESS |  | Not Started | Low | Riza Urmeneta |  | Job Stage
14. Confirm contract signings | JC02 - CONTRACTS PROCESS |  | Not Started | Low | Jed Smith |  | Job Stage
06. Prepare Terms & Conditions Sheet | JC02 - CONTRACTS PROCESS |  | Not Started | Low | Jed Smith |  | Job Stage
JC01 - ESTIMATION |  |  | Not Started | Low |  |  | Job Stage
01. Ensure Job Folder is set up in Google Drive | JC01 - ESTIMATION |  | Not Started | Low | Riza Urmeneta |  | Job Stage
02. Create E- Notes Sheet | JC01 - ESTIMATION |  | Not Started | Low |  |  | Job Stage
03. Confirm all documents received | JC01 - ESTIMATION |  | Not Started | Low |  |  | Job Stage
04. List missing or awaiting documents | JC01 - ESTIMATION |  | Not Started | Low |  |  | Job Stage
05. Sweeping review of plans (1 hour) | JC01 - ESTIMATION |  | Not Started | Low |  |  | Job Stage
06. Sweeping review of specifications | JC01 - ESTIMATION |  | Not Started | Low |  |  | Job Stage
07. Create RFI's | JC01 - ESTIMATION |  | Not Started | Low |  |  | Job Stage
08. Prepare & send PC Item RFQ's | JC01 - ESTIMATION |  | Not Started | Low |  |  | Job Stage
09. Schedule checkpoints x 3 | JC01 - ESTIMATION |  | Not Started | Low |  |  | Job Stage
10. Create Labour Estimate Sheet | JC01 - ESTIMATION |  | Not Started | Low |  |  | Job Stage
11. CATEGORY CHECKLIST MEETING | JC01 - ESTIMATION | Recommended 1 hour Happens prior to quoting, this is a brainstorming session. Best to have 2 team members involved. Confirm job stages listed in E-Notes &amp; Buildern. Work through the list of job stages, for each category, confirm whether the job stage is required. | Not Started | Low |  |  | Job Stage
12. SUBBIE QUOTES | JC01 - ESTIMATION | Complete measure &amp; scope for trades In Buildern, create or refine the scope required for each trade, including measurements/quantities wherever necessary. Prepare RFQs for all trades listed as requiring a quote in the E-Notes. Send all required RFQs. Save any subbie quotes to Job Folder &gt; Quotes In and name the document [{Trade} - {Business Name}] Move all old quotes to the archive folder Add calendar item to send a reminder to trades who have not | Not Started | Low |  |  | Job Stage
13. ESTIMATE E-NOTES | JC01 - ESTIMATION |  | Not Started | Low |  |  | Job Stage
14. TAKE OFF REVIEW | JC01 - ESTIMATION |  | Not Started | Low |  |  | Job Stage
15. QUOTE DELIVERY | JC01 - ESTIMATION |  | Not Started | Low |  |  | Job Stage
JC03 - JOB PREPARATION |  | https://docs.google.com/document/d/16CZV-kR6TarniWlP5T4uK-tYFXSvT4eFWI8X3FlSLB8/edit?tab=t.wms28hl7vuwz | Not Started | Low |  |  | Job Stage
01. Confirm Job Details in Buildern | JC03 - JOB PREPARATION |  | Not Started | Low | Riza Urmeneta |  | Job Stage
02. Lock Estimate & Cost Coding | JC03 - JOB PREPARATION |  | Not Started | Low | Riza Urmeneta |  | Job Stage
03. Add Employees To Job | JC03 - JOB PREPARATION |  | Not Started | Low | Riza Urmeneta |  | Job Stage
04. Apply for HBCF | JC03 - JOB PREPARATION |  | Not Started | Low | Jed Smith |  | Job Stage
07. Send Deposit & HBCF Invoice | JC03 - JOB PREPARATION |  | Not Started | Low | Riza Urmeneta |  | Job Stage
08. Create Job Schedule | JC03 - JOB PREPARATION |  | Not Started | Low | Jed Smith |  | Job Stage
09. Define Project Start Date | JC03 - JOB PREPARATION |  | Not Started | Low | Jed Smith |  | Job Stage
10. Schedule trades | JC03 - JOB PREPARATION |  | Not Started | Low | Jed Smith |  | Job Stage
15. Manage Materials & Orders | JC03 - JOB PREPARATION |  | Not Started | Low | Jed Smith |  | Job Stage
16. Prepare Site Plans | JC03 - JOB PREPARATION |  | Not Started | Low | Jed Smith |  | Job Stage
14. Create Scope of Works Sheet | JC03 - JOB PREPARATION |  | Not Started | Low | Jed Smith |  | Job Stage
25. Create Neighbour Notification Letter | JC03 - JOB PREPARATION |  | Not Started | Low | Riza Urmeneta |  | Job Stage
27. Coordinate Sub-Contractors | JC03 - JOB PREPARATION |  | Not Started | Low | Jed Smith |  | Job Stage
20. Create All Selections in Buildern | JC03 - JOB PREPARATION |  | Not Started | Low | Riza Urmeneta |  | Job Stage
21. Set Up Job Folders in Buildern | JC03 - JOB PREPARATION |  | Not Started | Low | Riza Urmeneta |  | Job Stage
22. Add Provisional Sums as Variations | JC03 - JOB PREPARATION |  | Not Started | Low | Riza Urmeneta |  | Job Stage
23. Confirm Selections Lead Times | JC03 - JOB PREPARATION |  | Not Started | Low | Riza Urmeneta |  | Job Stage
26. Organise Team Briefing | JC03 - JOB PREPARATION |  | Not Started | Low | Riza Urmeneta |  | Job Stage
17. Define Project Start Date | JC03 - JOB PREPARATION |  | Not Started | Low | Jed Smith |  | Job Stage
18. Introduce Office Manager | JC03 - JOB PREPARATION |  | Not Started | Low | Riza Urmeneta |  | Job Stage
28. Finalise Job Folder | JC03 - JOB PREPARATION |  | Not Started | Low | Riza Urmeneta |  | Job Stage
29. Project Manager Handover | JC03 - JOB PREPARATION |  | Not Started | Low | Jed Smith |  | Job Stage
30. Create Trade Specific Plans | JC03 - JOB PREPARATION |  | Not Started | Low | Jed Smith |  | Job Stage
31. Create Media Plan | JC03 - JOB PREPARATION |  | Not Started | Low | Jed Smith |  | Job Stage
13. Confirm Trades & Optimise Schedule | JC03 - JOB PREPARATION |  | Not Started | Low | Jed Smith |  | Job Stage
12. Create Trades Sub-Contracts & Suppliers Purchase Orders | JC03 - JOB PREPARATION |  | Not Started | Low | Jed Smith |  | Job Stage
11. Contact All Trade by Phone to Discuss Timeframes | JC03 - JOB PREPARATION |  | Not Started | Low | Jed Smith |  | Job Stage
24. Create Labour hours sheet from estimating sheet | JC03 - JOB PREPARATION |  | Not Started | Low | Riza Urmeneta |  | Job Stage
19. Add expenses to Allocated Overheads Sheet | JC03 - JOB PREPARATION |  | Not Started | Low | Riza Urmeneta |  | Job Stage
05 Confirm HCBF Approval | JC03 - JOB PREPARATION |  | Not Started | Low | Riza Urmeneta |  | Job Stage
06. Create Client Invoices | JC03 - JOB PREPARATION |  | Not Started | Low | Riza Urmeneta |  | Job Stage
02.1 Confirm Cost Codes | JC03 - JOB PREPARATION |  | Not Started | Low | Jed Smith |  | Job Stage
ITP01 - DILAPIDATION REPORT |  |  | Not Started | Low |  |  | On-Site Checklist
Record - Existing Conditions | ITP01 - DILAPIDATION REPORT | Record - Take clear photos and videos of the existing condition of all adjacent buildings, including walls, roofs, windows, doors, chimneys, fences, and any other external elements. Pay close attention to any existing cracks, damage, or signs of wear and tear. | Not Started | Low |  |  | On-Site Checklist
Record - Driveways, pathway, landscaping | ITP01 - DILAPIDATION REPORT | Record - Take clear photos and videos of driveways, pathways, and landscaping on adjacent properties. Capture the overall condition and any specific features or potential areas of concern. JP. Drone footage to get an over all snapshot. | Not Started | Low |  |  | On-Site Checklist
Record - Retaining walls, fence, adjoining proporties | ITP01 - DILAPIDATION REPORT | Record - Take clear photos and videos of retaining walls and fences on adjacent properties. Document their condition, including any signs of movement, cracking, or deterioration. | Not Started | Low |  |  | On-Site Checklist
Record - Existing damage or defects on adjacent properties | ITP01 - DILAPIDATION REPORT | Record - Take clear photos and videos of any existing damage or defects on adjacent properties. Use close-up shots to clearly show the extent of any damage. | Not Started | Low |  |  | On-Site Checklist
Record - The condition of roads and footpaths adjacent to the site | ITP01 - DILAPIDATION REPORT | Record - Take clear photos and videos of the condition of roads and footpaths adjacent to the site. Capture the overall condition, including any cracks, potholes, or uneven surfaces. | Not Started | Low |  |  | On-Site Checklist
Record - The condition of kerbs and gutters adjacent to the site | ITP01 - DILAPIDATION REPORT | Record - Take clear photos and videos of the condition of kerbs and gutters adjacent to the site. Document any damage or signs of wear and tear. | Not Started | Low |  |  | On-Site Checklist
Record - Any street furniture (e.g., light poles, signs) near the site | ITP01 - DILAPIDATION REPORT | Record - Take clear photos and videos of any street furniture (e.g., light poles, signs) near the site. Capture their condition and location. | Not Started | Low |  |  | On-Site Checklist
Record - trees and vegetation near the site | ITP01 - DILAPIDATION REPORT | Record - Take clear photos and videos of trees and vegetation near the site. Document their size, health, and proximity to the construction area. | Not Started | Low |  |  | On-Site Checklist
Record - existing cracks or damage | ITP01 - DILAPIDATION REPORT | Record - If there are any existing cracks or damage, write a detailed description of its condition and measure them. | Not Started | Low |  |  | On-Site Checklist
Acknowledgement - I confirm that I have personally inspected every item on this checklist | ITP01 - DILAPIDATION REPORT | Acknowledgement: I confirm that I have personally inspected every item on this checklist, all checks are accurate, and any issues have been addressed. I take full responsibility for the quality of this inspection. | Not Started | Low |  |  | On-Site Checklist
ITP03 - SITE SETUP AND EXCAVATION INSPECTION |  |  | Not Started | Low |  |  | On-Site Checklist
Inspect - Clear access to the site | ITP03 - SITE SETUP AND EXCAVATION INSPECTION | Inspect - Clear access to the site for construction vehicles and personnel. | Not Started | Low |  |  | On-Site Checklist
Inspect - Any necessary permits for road/traffic | ITP03 - SITE SETUP AND EXCAVATION INSPECTION | Inspect - Any necessary permits for road closures or traffic management are in place. | Not Started | Low |  |  | On-Site Checklist
Inspect - The installation of the site container | ITP03 - SITE SETUP AND EXCAVATION INSPECTION | Inspect - The installation of the site container, ensuring it is positioned safely and securely. | Not Started | Low |  |  | On-Site Checklist
Inspect - The installation of the site toilet | ITP03 - SITE SETUP AND EXCAVATION INSPECTION | Inspect - The installation of the site toilet, ensuring proper connection and sanitation. | Not Started | Low |  |  | On-Site Checklist
Inspect - That site fencing is erected securely | ITP03 - SITE SETUP AND EXCAVATION INSPECTION | Inspect - That site fencing is erected securely around the perimeter of the site. | Not Started | Low |  |  | On-Site Checklist
Inspect - That all required signage | ITP03 - SITE SETUP AND EXCAVATION INSPECTION | Inspect - That all required signage (Davies Branding, Emergency Assembly Point, Site Safety) is installed in prominent locations. | Not Started | Low |  |  | On-Site Checklist
Inspect - Safety Management Plan | ITP03 - SITE SETUP AND EXCAVATION INSPECTION | Inspect - That a Safety Management Plan is in place and readily accessible on-site. | Not Started | Low |  |  | On-Site Checklist
Inspect - Appropriate safety equipment | ITP03 - SITE SETUP AND EXCAVATION INSPECTION | Inspect - That appropriate safety equipment and first aid facilities are available. | Not Started | Low |  |  | On-Site Checklist
Inspect - Excavation area is clearly marked and set out | ITP03 - SITE SETUP AND EXCAVATION INSPECTION | Inspect - That the excavation area is clearly marked and set out according to the approved plans. | Not Started | Low |  |  | On-Site Checklist
Inspect - Any protective measures for adjacent structures or services | ITP03 - SITE SETUP AND EXCAVATION INSPECTION | Inspect - That any protective measures for adjacent structures or services are in place. | Not Started | Low |  |  | On-Site Checklist
Inspect - The property boundary pegs are clearly marked | ITP03 - SITE SETUP AND EXCAVATION INSPECTION | Inspect - The property boundary pegs are clearly marketed. | Not Started | Low |  |  | On-Site Checklist
Inspect - The building setout | ITP03 - SITE SETUP AND EXCAVATION INSPECTION | Inspect - The building setout, ensuring accurate positioning and alignment according to the approved plans. | Not Started | Low |  |  | On-Site Checklist
Inspect - That all necessary reference points and benchmarks are established | ITP03 - SITE SETUP AND EXCAVATION INSPECTION | Inspect - That all necessary reference points and benchmarks are established and clearly marked. | Not Started | Low |  |  | On-Site Checklist
Record - That "Dial Before You Dig" has been conducted and updated | ITP03 - SITE SETUP AND EXCAVATION INSPECTION | Record - That "Dial Before You Dig" has been conducted and updated. | Not Started | Low |  |  | On-Site Checklist
Inspect - That the site security cameras are set up | ITP03 - SITE SETUP AND EXCAVATION INSPECTION | Inspect - That the site security cameras are set up facing the correct area and working. | Not Started | Low |  |  | On-Site Checklist
Acknowledgement - I confirm that I have personally inspected every item on this checklist | ITP03 - SITE SETUP AND EXCAVATION INSPECTION | Acknowledgement: I confirm that I have personally inspected every item on this checklist, all checks are accurate, and any issues have been addressed. I take full responsibility for the quality of this inspection. | Not Started | Low |  |  | On-Site Checklist
ITP04 - FOUNDATION INSPECTION |  |  | Not Started | Low |  |  | On-Site Checklist
Inspect - Underslab plumbing | ITP04 - FOUNDATION INSPECTION | Inspect - Underslab plumbing is complete. | Not Started | Low |  |  | On-Site Checklist
Inspect - Electrical lead-in conduits | ITP04 - FOUNDATION INSPECTION | Inspect - Electrical lead-in conduits are installed. | Not Started | Low |  |  | On-Site Checklist
Inspect - Water lead-in | ITP04 - FOUNDATION INSPECTION | Inspect - Water lead-in is installed. | Not Started | Low |  |  | On-Site Checklist
Inspect - Phone/NBN lead-in | ITP04 - FOUNDATION INSPECTION | Inspect - Phone/NBN lead-in is installed. | Not Started | Low |  |  | On-Site Checklist
Inspect - Base gravel compaction | ITP04 - FOUNDATION INSPECTION | Inspect - Base gravel is compacted in layers and to the correct level. | Not Started | Low |  |  | On-Site Checklist
Inspect - Footing construction | ITP04 - FOUNDATION INSPECTION | Inspect - Footings are positioned and constructed according to the approved plans. | Not Started | Low |  |  | On-Site Checklist
Inspect - Reinforcement placement | ITP04 - FOUNDATION INSPECTION | Inspect - Reinforcement is placed correctly in accordance with the approved plans. | Not Started | Low |  |  | On-Site Checklist
Inspect - Foundation heights and dimensions | ITP04 - FOUNDATION INSPECTION | Inspect - Foundation heights and dimensions are accurate. | Not Started | Low |  |  | On-Site Checklist
Inspect - Slab setdowns | ITP04 - FOUNDATION INSPECTION | Inspect - Slab setdowns are correctly positioned and constructed. | Not Started | Low |  |  | On-Site Checklist
Inspect - Formwork setup | ITP04 - FOUNDATION INSPECTION | Inspect - Form work is straight and securely braced before placing concrete. | Not Started | Low |  |  | On-Site Checklist
Inspect - Reinforcement clearance at rebates | ITP04 - FOUNDATION INSPECTION | Inspect - Reinforcment clearance is achieved where windows and doors are to be rebated into concrete. | Not Started | Low |  |  | On-Site Checklist
Record - Building surveyor reinforcement approval | ITP04 - FOUNDATION INSPECTION | Record - Building surveyor has inspected and approved the reinforcement. | Not Started | Low |  |  | On-Site Checklist
Record - Matterport reinforcement scan | ITP04 - FOUNDATION INSPECTION | Record - Matterport scan of completed reinforcement before placing concrete. | Not Started | Low |  |  | On-Site Checklist
Test - Concrete slump | ITP04 - FOUNDATION INSPECTION | Test: The concrete slump for project with appearance concrete. Maximum 100mm slump. Add photo of slump test results. | Not Started | Low |  |  | On-Site Checklist
Inspect - Slab Curing | ITP04 - FOUNDATION INSPECTION | Inspect - Concrete slab has been flooded with water to cure for 21 days with formwork remaining to slow edge drying. | Not Started | Low |  |  | On-Site Checklist
Acknowledgement: Inspector confirmation of completed inspection accuracy and acceptance of responsibility | ITP04 - FOUNDATION INSPECTION | Acknowledgement: I confirm that I have personally inspected every item on this checklist, all checks are accurate, and any issues have been addressed. I take full responsibility for the quality of this inspection. | Not Started | Low |  |  | On-Site Checklist
ITP05 - FRAME INSPECTION |  |  | Not Started | Low |  |  | On-Site Checklist
Inspect - Frame set-out accuracy | ITP05 - FRAME INSPECTION | Inspect - The frame is set out accurately according to the approved plans. | Not Started | Low |  |  | On-Site Checklist
Inspect - Plumb and straight framing members | ITP05 - FRAME INSPECTION | Inspect - All framing members are plumb and straight. | Not Started | Low |  |  | On-Site Checklist
Inspect - Strapping and bracing installation | ITP05 - FRAME INSPECTION | Inspect - All strapping and bracing is installed correctly. | Not Started | Low |  |  | On-Site Checklist
Inspect - Frame fixing compliance | ITP05 - FRAME INSPECTION | Inspect - The frame is adequately fixed (dyna-bolted or as per engineering requirements). | Not Started | Low |  |  | On-Site Checklist
Inspect - Manhole framing | ITP05 - FRAME INSPECTION | Inspect - The manhole is framed correctly. | Not Started | Low |  |  | On-Site Checklist
Inspect - Cavity sliders and door jambs | ITP05 - FRAME INSPECTION | Inspect - Cavity sliders and door jambs are installed and plumb. | Not Started | Low |  |  | On-Site Checklist
Inspect - Wet area noggins | ITP05 - FRAME INSPECTION | Inspect - Noggins are fitted in wet areas for fixtures and to comply with liveable housing standards (toilet roll holder, towel rails, etc.). | Not Started | Low |  |  | On-Site Checklist
Inspect - Garage door noggins | ITP05 - FRAME INSPECTION | Inspect - Noggins are fitted for the garage door. | Not Started | Low |  |  | On-Site Checklist
Inspect - Ceiling batten noggins | ITP05 - FRAME INSPECTION | Inspect - Noggins are fitted for ceiling battens. | Not Started | Low |  |  | On-Site Checklist
Inspect - Structural steel approval | ITP05 - FRAME INSPECTION | Inspect - Structural steel is inspected and approved. | Not Started | Low |  |  | On-Site Checklist
Inspect - Stud marking for plasterer | ITP05 - FRAME INSPECTION | Inspect - Studs are marked for the plasterer. | Not Started | Low |  |  | On-Site Checklist
Inspect - Roof frame and battens | ITP05 - FRAME INSPECTION | Inspect - The roof frame is complete with battens screwed. | Not Started | Low |  |  | On-Site Checklist
Record - Building surveyor frame approval | ITP05 - FRAME INSPECTION | Record - Building surveyor has inspected and approved the frame. | Not Started | Low |  |  | On-Site Checklist
Record - Matterport frame scan | ITP05 - FRAME INSPECTION | Record - Matterport scan of completed floor, walls and roof frames before installing insulation. | Not Started | Low |  |  | On-Site Checklist
Inspect - Frame finish and workmanship | ITP05 - FRAME INSPECTION | Inspect - Frame for any unsightly fixings, timber with mould and meets the Davies standard of quality workmanship. | Not Started | Low |  |  | On-Site Checklist
Inspect - Fixing material compliance | ITP05 - FRAME INSPECTION | Inspect - That all fixings are galvernized or stainless steel where needed. | Not Started | Low |  |  | On-Site Checklist
Inspect - Damp course and treated timbers | ITP05 - FRAME INSPECTION | Inspect - That damp course and treated timbers are used where needed. | Not Started | Low |  |  | On-Site Checklist
Inspect - Wall straightness for finishes | ITP05 - FRAME INSPECTION | Inspect - That all walls are straitened and ready for plaster and joinery. | Not Started | Low |  |  | On-Site Checklist
Inspect - Roof cavity service access | ITP05 - FRAME INSPECTION | Inspect - That roof cavity has access for services eg. platform around manhole. | Not Started | Low |  |  | On-Site Checklist
Acknowledgement: Inspector confirmation of completed inspection accuracy and acceptance of responsibility | ITP05 - FRAME INSPECTION | Acknowledgement: I confirm that I have personally inspected every item on this checklist, all checks are accurate, and any issues have been addressed. I take full responsibility for the quality of this inspection. | Not Started | Low |  |  | On-Site Checklist
ITP06 - BUILDING ENVELOPE - WEATHER TIGHTNESS INSPECTION |  |  | Not Started | Low |  |  | On-Site Checklist
Inspect - Weather-resistant membrane installation | ITP06 - BUILDING ENVELOPE - WEATHER TIGHTNESS INSPECTION | Inspect - The installation of the weather-resistant membrane, ensuring it is continuous, properly lapped, and sealed at all penetrations. | Not Started | Low |  |  | On-Site Checklist
Inspect - Flashings around openings | ITP06 - BUILDING ENVELOPE - WEATHER TIGHTNESS INSPECTION | Inspect - The installation of flashings around windows, doors, and other openings, ensuring they are correctly positioned and sealed to prevent water ingress. | Not Started | Low |  |  | On-Site Checklist
Inspect - Sealing of joints and seams | ITP06 - BUILDING ENVELOPE - WEATHER TIGHTNESS INSPECTION | Inspect - The sealing of all joints and seams in the membrane and flashings, using appropriate sealants and tapes. | Not Started | Low |  |  | On-Site Checklist
Inspect - Window and door frame installation | ITP06 - BUILDING ENVELOPE - WEATHER TIGHTNESS INSPECTION | Inspect - The installation of window and door frames, ensuring they are properly sealed and weatherstripped. | Not Started | Low |  |  | On-Site Checklist
Test: Conduct Hose test for water penetration | ITP06 - BUILDING ENVELOPE - WEATHER TIGHTNESS INSPECTION | Test: Conduct a hose test to simulate wind-driven rain, spraying water onto the building envelope from various angles to check for any signs of water penetration. | Not Started | Low |  |  | On-Site Checklist
Inspect - The drainage plane behind the cladding | ITP06 - BUILDING ENVELOPE - WEATHER TIGHTNESS INSPECTION | Inspect - The drainage plane behind the cladding, ensuring it is clear and allows for proper drainage of any water that may penetrate the cladding. | Not Started | Low |  |  | On-Site Checklist
Inspect - Sealant joints and weatherstripping condition | ITP06 - BUILDING ENVELOPE - WEATHER TIGHTNESS INSPECTION | Inspect - The condition of sealant joints and weatherstripping around windows and doors, ensuring they are intact and provide an effective seal. | Not Started | Low |  |  | On-Site Checklist
Record - Water penetration observations | ITP06 - BUILDING ENVELOPE - WEATHER TIGHTNESS INSPECTION | Record - Any areas where water penetration is observed during the hose test or visual inspection. | Not Started | Low |  |  | On-Site Checklist
Record - Deficiencies in weatherproofing installation | ITP06 - BUILDING ENVELOPE - WEATHER TIGHTNESS INSPECTION | Record - Any deficiencies in the installation of the weather-resistant barrier, flashings, or sealants. | Not Started | Low |  |  | On-Site Checklist
Inspect - Air flow requirements | ITP06 - BUILDING ENVELOPE - WEATHER TIGHTNESS INSPECTION | Inspect - Air flow requirements are being met eg. ridges, gable end vents, rafter end vents and parallel chord vaulted trusses. | Not Started | Low |  |  | On-Site Checklist
Acknowledgement: Inspector confirmation of completed inspection accuracy and acceptance of responsibility | ITP06 - BUILDING ENVELOPE - WEATHER TIGHTNESS INSPECTION | Acknowledgement: I confirm that I have personally inspected every item on this checklist, all checks are accurate, and any issues have been addressed. I take full responsibility for the quality of this inspection. | Not Started | Low |  |  | On-Site Checklist
ITP07 - BUILDING ENVELOPE - CLADDING/RAINSCREEN INSPECTION |  |  | Not Started | Low |  |  | On-Site Checklist
Inspect - Cladding installation per drawings and AS codes | ITP07 - BUILDING ENVELOPE - CLADDING/RAINSCREEN INSPECTION | Inspect - Verify that the cladding is installed in accordance with the manufacturer's instructions and the approved drawings. (e.g., AS 4055 Wind Loads, AS/NZS 4284 Water Penetration) | Not Started | Low |  |  | On-Site Checklist
Inspect - Cladding alignment, spacing and fixing | ITP07 - BUILDING ENVELOPE - CLADDING/RAINSCREEN INSPECTION | Inspect - Check for proper alignment, spacing, and fixing of cladding elements. | Not Started | Low |  |  | On-Site Checklist
Inspect - Cladding joints and overlaps weathertightness | ITP07 - BUILDING ENVELOPE - CLADDING/RAINSCREEN INSPECTION | Inspect - Ensure that all joints and overlaps are correctly sealed and weathertight. | Not Started | Low |  |  | On-Site Checklist
Inspect - Cladding ground and element clearance compliance | ITP07 - BUILDING ENVELOPE - CLADDING/RAINSCREEN INSPECTION | Inspect - Confirm that the cladding is installed with the correct clearances from the ground and other building elements (e.g., windows, doors). | Not Started | Low |  |  | On-Site Checklist
Inspect - Flashings installation for water protection | ITP07 - BUILDING ENVELOPE - CLADDING/RAINSCREEN INSPECTION | Inspect - Verify that all flashings (e.g., window head flashings, sill flashings, corner flashings) are installed correctly to prevent water penetration. | Not Started | Low |  |  | On-Site Checklist
Inspect - Flashings lapping and sealing continuity | ITP07 - BUILDING ENVELOPE - CLADDING/RAINSCREEN INSPECTION | Inspect - Ensure that flashings are lapped and sealed correctly to maintain continuity of the water barrier. | Not Started | Low |  |  | On-Site Checklist
Inspect - Flashings compatibility with cladding | ITP07 - BUILDING ENVELOPE - CLADDING/RAINSCREEN INSPECTION | Inspect - Confirm that flashings are compatible with the cladding material | Not Started | Low |  |  | On-Site Checklist
Inspect - Flashings installation compliance with manufacture's instruction | ITP07 - BUILDING ENVELOPE - CLADDING/RAINSCREEN INSPECTION | Inspect - Confirm that flashings are are installed in accordance with the manufacturer's instructions. | Not Started | Low |  |  | On-Site Checklist
Inspect - Cavity width and obstruction-free verification | ITP07 - BUILDING ENVELOPE - CLADDING/RAINSCREEN INSPECTION | Inspect - Verify that the cavity between the cladding and the weather-resistant barrier is of the correct width and is free from obstructions. | Not Started | Low |  |  | On-Site Checklist
Inspect - Ventilation openings top and bottom of cavity | ITP07 - BUILDING ENVELOPE - CLADDING/RAINSCREEN INSPECTION | Inspect - Confirm that ventilation openings (e.g., weep holes, vents) are provided at the top and bottom of the cavity to allow for drainage and airflow. | Not Started | Low |  |  | On-Site Checklist
Inspect - Ventilation openings insect screen protection | ITP07 - BUILDING ENVELOPE - CLADDING/RAINSCREEN INSPECTION | Inspect - Ensure that the ventilation openings are protected with insect screens or other suitable measures to prevent pest entry. | Not Started | Low |  |  | On-Site Checklist
Inspect - Cladding BAL compliance | ITP07 - BUILDING ENVELOPE - CLADDING/RAINSCREEN INSPECTION | Inspect - If the building is located in a bushfire-prone area, verify that the cladding and other building elements comply with the relevant bushfire attack level (BAL) requirements. | Not Started | Low |  |  | On-Site Checklist
Inspect - Ember guards and fire safety measures installed | ITP07 - BUILDING ENVELOPE - CLADDING/RAINSCREEN INSPECTION | Inspect - Confirm that appropriate ember guards and other fire safety measures are installed. | Not Started | Low |  |  | On-Site Checklist
Inspect - Rodent protection mesh and barrier installation | ITP07 - BUILDING ENVELOPE - CLADDING/RAINSCREEN INSPECTION | Inspect - Verify that measures are in place to prevent rodent entry into the building envelope, such as the use of rodent mesh or other barriers at the base of the cladding and around any penetrations. | Not Started | Low |  |  | On-Site Checklist
Inspect - Fixings and fasteners compatibility with cladding and coastal environment suitability | ITP07 - BUILDING ENVELOPE - CLADDING/RAINSCREEN INSPECTION | Inspect - Verify that all fixings and fasteners used in the cladding system are compatible with the cladding material and are suitable for the coastal environment. | Not Started | Low |  |  | On-Site Checklist
Inspect - Stainless steel fixings in tide zone compliance | ITP07 - BUILDING ENVELOPE - CLADDING/RAINSCREEN INSPECTION | Inspect - Confirm that stainless steel fixings are used in areas within [insert distance from breaking tide based on building code] of the breaking tide, as required by the building code. | Not Started | Low |  |  | On-Site Checklist
Inspect - Galvanized fixings corrosion rating compliance | ITP07 - BUILDING ENVELOPE - CLADDING/RAINSCREEN INSPECTION | Inspect - Confirm that galvanized fixings used in areas outside the stainless steel zone meet the required corrosion resistance rating for the specific location and exposure conditions (refer to the building code and manufacturer's specifications). | Not Started | Low |  |  | On-Site Checklist
Inspect - Cladding finish surface prep (paint/sealer/oil) | ITP07 - BUILDING ENVELOPE - CLADDING/RAINSCREEN INSPECTION | Inspect - Claddings that are to be finnished with paint, sealer or oil, ensure that they are clean, sanded and free from defects. | Not Started | Low |  |  | On-Site Checklist
Acknowledgement: Inspector confirmation of completed inspection accuracy and acceptance of responsibility | ITP07 - BUILDING ENVELOPE - CLADDING/RAINSCREEN INSPECTION | Acknowledgement: I confirm that I have personally inspected every item on this checklist, all checks are accurate, and any issues have been addressed. I take full responsibility for the quality of this inspection. | Not Started | Low |  |  | On-Site Checklist
ITP08 - EXTERNAL DOORS AND WINDOWS COMPLETION |  |  | Not Started | Low |  |  | On-Site Checklist
Inspect - Smooth operation of windows and doors | ITP08 - EXTERNAL DOORS AND WINDOWS COMPLETION | Inspect - All external windows and doors operate smoothly without binding or sticking. | Not Started | Low |  |  | On-Site Checklist
Inspect - Frame alignment | ITP08 - EXTERNAL DOORS AND WINDOWS COMPLETION | Inspect - Window and door frames are installed squarely, plumb, and level in their openings. | Not Started | Low |  |  | On-Site Checklist
Inspect - Gaps and clearances | ITP08 - EXTERNAL DOORS AND WINDOWS COMPLETION | Inspect - Gaps and clearances around windows and doors are consistent and meet specifications. Pay close attention to door thresholds and weatherstripping. | Not Started | Low |  |  | On-Site Checklist
Inspect - Hardware installation | ITP08 - EXTERNAL DOORS AND WINDOWS COMPLETION | Inspect - All hardware (locks, handles, hinges) is installed correctly, functions properly, and is free from damage. | Not Started | Low |  |  | On-Site Checklist
Inspect - Locks and keys | ITP08 - EXTERNAL DOORS AND WINDOWS COMPLETION | Inspect - Locks and keys are organized, labeled, and in one location for each window and door, including flyscreens. | Not Started | Low |  |  | On-Site Checklist
Inspect - Glazing | ITP08 - EXTERNAL DOORS AND WINDOWS COMPLETION | Inspect - Window glazing is installed correctly, is free from damage, and provides a weathertight seal. | Not Started | Low |  |  | On-Site Checklist
Inspect - External finishes | ITP08 - EXTERNAL DOORS AND WINDOWS COMPLETION | Inspect - External finishes (e.g., paint, sealant) are complete and to a high standard, with no gaps or cracks. | Not Started | Low |  |  | On-Site Checklist
Inspect - Weatherproofing | ITP08 - EXTERNAL DOORS AND WINDOWS COMPLETION | Inspect - Windows and doors are free from drafts and excessive air leakage. | Not Started | Low |  |  | On-Site Checklist
Inspect - Security screens | ITP08 - EXTERNAL DOORS AND WINDOWS COMPLETION | Inspect - Security screens (if applicable) are installed correctly and operate smoothly | Not Started | Low |  |  | On-Site Checklist
Inspect - Drainage and weep holes | ITP08 - EXTERNAL DOORS AND WINDOWS COMPLETION | Inspect - All weep holes and drainage provisions are clear and functioning correctly. | Not Started | Low |  |  | On-Site Checklist
Inspect - Damage check | ITP08 - EXTERNAL DOORS AND WINDOWS COMPLETION | Inspect - Windows, doors, and thresholds are free from damage caused by foot traffic, tools, or materials. | Not Started | Low |  |  | On-Site Checklist
Acknowledgement: Inspector confirmation of completed inspection accuracy and acceptance of responsibility | ITP08 - EXTERNAL DOORS AND WINDOWS COMPLETION | Acknowledgement: I confirm that I have personally inspected every item on this checklist, all checks are accurate, and any issues have been addressed. I take full responsibility for the quality of this inspection. | Not Started | Low |  |  | On-Site Checklist
ITP09 - BUILDING ENVELOPE - AIRTIGHTNESS INSPECTION |  |  | Not Started | Low |  |  | On-Site Checklist
Inspect - Openings and holes seals | ITP09 - BUILDING ENVELOPE - AIRTIGHTNESS INSPECTION | Inspect - Confirm all openings and holes are sealed up. | Not Started | Low |  |  | On-Site Checklist
Test: Airtightness through Blower door test | ITP09 - BUILDING ENVELOPE - AIRTIGHTNESS INSPECTION | Test: Conduct a blower door test in accordance with AS/NZS ISO 9972 to measure the airtightness of the building envelope. | Not Started | Low |  |  | On-Site Checklist
Record - Building volume | ITP09 - BUILDING ENVELOPE - AIRTIGHTNESS INSPECTION | Record - The building volume (cubic meters). | Not Started | Low |  |  | On-Site Checklist
Record - Airflow rate at 50 Pa | ITP09 - BUILDING ENVELOPE - AIRTIGHTNESS INSPECTION | Record - The airflow rate at 50 Pa (cubic meters per hour). | Not Started | Low |  |  | On-Site Checklist
Record - ACH50 value | ITP09 - BUILDING ENVELOPE - AIRTIGHTNESS INSPECTION | Record - The calculated ACH50 (air changes per hour at 50 Pascals). | Not Started | Low |  |  | On-Site Checklist
Inspect - Airtightness results vs targets | ITP09 - BUILDING ENVELOPE - AIRTIGHTNESS INSPECTION | Inspect - The results against the project target or relevant building code requirements. Older, Unsealed Homes: Can be as high as 10 to 20 ACH50 or even more. New Homes Built to Code: Aim for 5 to 7 ACH50 (Lower than 5 ACH50 mechanical ventilation is highly recommended). High-Performance Homes: Achieve 3 ACH50 or lower (Lower than 3 ACH50 will trigger mandatory mechanical ventilation). Certified Passivhaus: Achieve 0.6 ACH50 or lower. | Not Started | Low |  |  | On-Site Checklist
Inspect - Leakage pathways | ITP09 - BUILDING ENVELOPE - AIRTIGHTNESS INSPECTION | Inspect (if necessary): Use smoke pencils or other methods to identify and document any major air leakage pathways. | Not Started | Low |  |  | On-Site Checklist
Record - Blower door test evidence | ITP09 - BUILDING ENVELOPE - AIRTIGHTNESS INSPECTION | Record - Add photo of the blower door test results. | Not Started | Low |  |  | On-Site Checklist
Acknowledgement: Inspector confirmation of completed inspection accuracy and acceptance of responsibility | ITP09 - BUILDING ENVELOPE - AIRTIGHTNESS INSPECTION | Acknowledgement: I confirm that I have personally inspected every item on this checklist, all checks are accurate, and any issues have been addressed. I take full responsibility for the quality of this inspection. | Not Started | Low |  |  | On-Site Checklist
ITP10 - INSULATION INSPECTION |  |  | Not Started | Low |  |  | On-Site Checklist
Inspect - Insulation coverage installation | ITP10 - INSULATION INSPECTION | Inspect - Confirm that insulation is installed in all required areas (walls, ceilings, roof spaces) with full coverage and no gaps. | Not Started | Low |  |  | On-Site Checklist
Inspect - Insulation condition | ITP10 - INSULATION INSPECTION | Inspect - Check for any signs of compression or damage to the insulation. | Not Started | Low |  |  | On-Site Checklist
Inspect - Insulation density and R-value | ITP10 - INSULATION INSPECTION | Inspect - Ensure that insulation is installed at the correct density and R-value. | Not Started | Low |  |  | On-Site Checklist
Inspect - Insulation penetrations sealing | ITP10 - INSULATION INSPECTION | Inspect - Ensure that all penetrations through the insulation are sealed properly. | Not Started | Low |  |  | On-Site Checklist
Record - Matterport scan before linings | ITP10 - INSULATION INSPECTION | Record - Confirm Matterport scan of completed floor, wall and ceiling insulation before installing internal linings. | Not Started | Low |  |  | On-Site Checklist
Record - Thermal bridging inspection | ITP10 - INSULATION INSPECTION | Record - Confirm inspect for thermal bridging issues. Thermal camera inspection, add photos. | Not Started | Low |  |  | On-Site Checklist
Inspect - Stud flush installation | ITP10 - INSULATION INSPECTION | Inspect - That all insulation is behind or flush with studs to prevent plaster bowing. | Not Started | Low |  |  | On-Site Checklist
Inspect - Subfloor insulation support | ITP10 - INSULATION INSPECTION | Inspect - That subfloor insulation is held into position appropriately to prevent sagging and falling out. | Not Started | Low |  |  | On-Site Checklist
Acknowledgement: Inspector confirmation of completed inspection accuracy and acceptance of responsibility | ITP10 - INSULATION INSPECTION | Acknowledgement: I confirm that I have personally inspected every item on this checklist, all checks are accurate, and any issues have been addressed. I take full responsibility for the quality of this inspection. | Not Started | Low |  |  | On-Site Checklist
ITP11 - INTERNAL LININGS INSPECTION |  |  | Not Started | Low |  |  | On-Site Checklist
Inspect - Plasterboard installation and fixing | ITP11 - INTERNAL LININGS INSPECTION | Inspect - Confirm plasterboard is installed correctly with proper fixing, ensuring it is level and securely attached. | Not Started | Low |  |  | On-Site Checklist
Inspect - Plasterboard surface condition | ITP11 - INTERNAL LININGS INSPECTION | Inspect - Ensure that the plasterboard is free from damage and is prepared adequately for painting (e.g., no nail pops, screw heads protruding). | Not Started | Low |  |  | On-Site Checklist
Inspect - Plasterboard joints and finishes | ITP11 - INTERNAL LININGS INSPECTION | Inspect - Check that the joints between plasterboard sheets are properly taped, filled, and sanded to create a smooth and even surface. | Not Started | Low |  |  | On-Site Checklist
Inspect - Cornices and plasterboard moldings | ITP11 - INTERNAL LININGS INSPECTION | Inspect - Verify that all cornices and other plasterboard moldings are installed correctly and are free from defects. | Not Started | Low |  |  | On-Site Checklist
Inspect - Wall and ceiling linings clearance | ITP11 - INTERNAL LININGS INSPECTION | Inspect - All wall and ceiling linings for bows and that no insulation or cables are caught behind. | Not Started | Low |  |  | On-Site Checklist
Inspect - Electrical service provisions | ITP11 - INTERNAL LININGS INSPECTION | Inspect - That all power and light cables are bought through or properly marked where needed. | Not Started | Low |  |  | On-Site Checklist
Inspect - Timber linings and paneling installation | ITP11 - INTERNAL LININGS INSPECTION | Inspect - All timber linings and paneling is installed with adequate expansion gaps, tight joints and correct fixings. | Not Started | Low |  |  | On-Site Checklist
Inspect - Plaster window reveals and beads | ITP11 - INTERNAL LININGS INSPECTION | Inspect - All plaster window reveals and beeds like externals and tear away are secured properly to prevent cracking (special attention to window reveals ). | Not Started | Low |  |  | On-Site Checklist
Acknowledgement: Inspector confirmation of completed inspection accuracy and acceptance of responsibility | ITP11 - INTERNAL LININGS INSPECTION | Acknowledgement: I confirm that I have personally inspected every item on this checklist, all checks are accurate, and any issues have been addressed. I take full responsibility for the quality of this inspection. | Not Started | Low |  |  | On-Site Checklist
ITP12 - INTERNAL FINISHES AND FIXTURES INSPECTION |  |  | Not Started | Low |  |  | On-Site Checklist
Inspect - Internal doors and frames installation | ITP12 - INTERNAL FINISHES AND FIXTURES INSPECTION | Inspect - Confirm that all internal doors and door frames are installed correctly with apropriate floor clearance and margins, operate smoothly, and have the appropriate hardware (handles, hinges, locks, soft closers and guides). | Not Started | Low |  |  | On-Site Checklist
Inspect - Skirting boards and architraves | ITP12 - INTERNAL FINISHES AND FIXTURES INSPECTION | Inspect - Verify that all skirting boards and architraves are installed neatly and are straight and free from damage. | Not Started | Low |  |  | On-Site Checklist
Inspect - Internal fixtures and fittings installation | ITP12 - INTERNAL FINISHES AND FIXTURES INSPECTION | Inspect - Check that all internal fixtures (e.g., light fittings, power points, switches, exhaust fans) are installed correctly and are in the correct locations. | Not Started | Low |  |  | On-Site Checklist
Inspect - Floor finishes installation | ITP12 - INTERNAL FINISHES AND FIXTURES INSPECTION | Inspect - Verify that all floor finishes (e.g., vinyl tiles, timber flooring, carpet) are installed correctly and meet specifications. | Not Started | Low |  |  | On-Site Checklist
Inspect - Wall finishes application | ITP12 - INTERNAL FINISHES AND FIXTURES INSPECTION | Inspect - Confirm that all wall finishes (e.g., paint, wallpaper) are applied evenly and to a high standard, with no visible defects. | Not Started | Low |  |  | On-Site Checklist
Inspect - Bathroom fixtures and shower screens | ITP12 - INTERNAL FINISHES AND FIXTURES INSPECTION | Inspect - Verify that shower screens and other bathroom fixtures are installed correctly and meet specifications. | Not Started | Low |  |  | On-Site Checklist
Inspect - Sealant joints workmanship | ITP12 - INTERNAL FINISHES AND FIXTURES INSPECTION | Inspect - Confirm that all sealant joints (e.g., around windows, doors, skirting boards) are neat and tidy, providing an effective seal. | Not Started | Low |  |  | On-Site Checklist
Inspect - Sliding doors and windows operation | ITP12 - INTERNAL FINISHES AND FIXTURES INSPECTION | Inspect - All external sliding doors and windows ailgn with closing side, latch and lock as intended. | Not Started | Low |  |  | On-Site Checklist
Inspect - Internal specifications compliance (LOO) | ITP12 - INTERNAL FINISHES AND FIXTURES INSPECTION | Inspect - All LOO internal specifications and fixtures are correct. | Not Started | Low |  |  | On-Site Checklist
Inspect - Accessories and fittings alignment | ITP12 - INTERNAL FINISHES AND FIXTURES INSPECTION | Inspect - All towel, toilet, robe, hanging fixtures are symmetrical, straight and level. | Not Started | Low |  |  | On-Site Checklist
Acknowledgement: Inspector confirmation of completed inspection accuracy and acceptance of responsibility | ITP12 - INTERNAL FINISHES AND FIXTURES INSPECTION | Acknowledgement: I confirm that I have personally inspected every item on this checklist, all checks are accurate, and any issues have been addressed. I take full responsibility for the quality of this inspection. | Not Started | Low |  |  | On-Site Checklist
ITP13 - JOINERY COMPLETION |  |  | Not Started | Low |  |  | On-Site Checklist
Inspect - Cabinet installation | ITP13 - JOINERY COMPLETION | Inspect - All cabinets are installed level and plumb, with consistent reveals and even gaps. | Not Started | Low |  |  | On-Site Checklist
Inspect - Doors, drawers, and hardware | ITP13 - JOINERY COMPLETION | Inspect - Doors and drawers operate smoothly, have consistent gaps, and align correctly. All hardware (hinges, handles, drawer runners) is present and functions correctly. | Not Started | Low |  |  | On-Site Checklist
Inspect - Shelves installation | ITP13 - JOINERY COMPLETION | Inspect - Shelves are securely installed and adjustable. | Not Started | Low |  |  | On-Site Checklist
Inspect - Benchtop installation | ITP13 - JOINERY COMPLETION | Inspect - Benchtops are installed level and securely fixed to the cabinets, with no gaps between the benchtop and walls. | Not Started | Low |  |  | On-Site Checklist
Inspect - Splashback installation | ITP13 - JOINERY COMPLETION | Inspect - Splashbacks are installed correctly and sealed to prevent water damage. | Not Started | Low |  |  | On-Site Checklist
Inspect - Appliance installation and function | ITP13 - JOINERY COMPLETION | Inspect - Appliances (oven, cooktop, rangehood, dishwasher) are installed correctly and are functional. Test the rangehood and dishwasher operation. | Not Started | Low |  |  | On-Site Checklist
Inspect - Dishwasher fixing and alignment | ITP13 - JOINERY COMPLETION | Inspect - The dishwasher is fixed into position and aligned correctly. | Not Started | Low |  |  | On-Site Checklist
Inspect - Sink installation and sealing | ITP13 - JOINERY COMPLETION | Inspect - Sinks are installed correctly and sealed to prevent water damage. | Not Started | Low |  |  | On-Site Checklist
Inspect - Joinery quality | ITP13 - JOINERY COMPLETION | Inspect - All joinery is free from damage, chips, and pencil/ink marks, and meets the specified quality standards. | Not Started | Low |  |  | On-Site Checklist
Inspect - Joints and edges finish | ITP13 - JOINERY COMPLETION | Inspect - All joints and edges are smooth and well-finished, with no visible chips or damage to edge taping. | Not Started | Low |  |  | On-Site Checklist
Inspect - Surfaces cleanliness | ITP13 - JOINERY COMPLETION | Inspect - All surfaces are clean and free from dust and debris. | Not Started | Low |  |  | On-Site Checklist
Inspect - Screw caps installation | ITP13 - JOINERY COMPLETION | Inspect - All screw caps are in place and match the surrounding finish. | Not Started | Low |  |  | On-Site Checklist
Inspect - Service penetrations | ITP13 - JOINERY COMPLETION | Inspect - All penetrations for pipes and cables are neat and tidy. | Not Started | Low |  |  | On-Site Checklist
Inspect - Joinery floor connection | ITP13 - JOINERY COMPLETION | Inspect - The joinery connection to the floor is neat and tidy, with no gaps or unevenness. | Not Started | Low |  |  | On-Site Checklist
Acknowledgement: Inspector confirmation of completed inspection accuracy and acceptance of responsibility | ITP13 - JOINERY COMPLETION | Acknowledgement: I confirm that I have personally inspected every item on this checklist, all checks are accurate, and any issues have been addressed. I take full responsibility for the quality of this inspection. | Not Started | Low |  |  | On-Site Checklist
ITP14 - WATERPROOFING INSPECTION |  |  | Not Started | Low |  |  | On-Site Checklist
Inspect - Compliance with AS 3740 and specs | ITP14 - WATERPROOFING INSPECTION | Inspect - Confirm the waterproofing complies with AS 3740-2010 Waterproofing of Wet Areas, manufacturer's specifications for waterproofing membrane and project drawings detailing wet area layout and waterproofing requirements | Not Started | Low |  |  | On-Site Checklist
Inspect - Substrate condition | ITP14 - WATERPROOFING INSPECTION | Inspect - Verify that the substrate (floor and wall surfaces) is clean, dry, and free from dust, debris, grease, and other contaminants that could affect adhesion. | Not Started | Low |  |  | On-Site Checklist
Inspect - Substrate repairs | ITP14 - WATERPROOFING INSPECTION | Inspect - Confirm that any cracks, holes, or imperfections in the substrate have been repaired in accordance with the manufacturer's instructions. | Not Started | Low |  |  | On-Site Checklist
Inspect - Priming | ITP14 - WATERPROOFING INSPECTION | Inspect - Verify that the substrate has been primed with the appropriate primer as per the manufacturer's specifications. Allow the primer to dry completely before applying the membrane and does not ecceed the dry time to apply time. | Not Started | Low |  |  | On-Site Checklist
Record - Substrate details | ITP14 - WATERPROOFING INSPECTION | Record - Note the type of substrate (e.g., concrete, screed, compressed sheeting) and its condition. | Not Started | Low |  |  | On-Site Checklist
Test: Substrate moisture | ITP14 - WATERPROOFING INSPECTION | Test: If necessary, use a moisture meter to measure the moisture content of the substrate and record the readings. Ensure the moisture content is within the acceptable range specified by the membrane manufacturer. | Not Started | Low |  |  | On-Site Checklist
Inspect - Membrane condition and batch | ITP14 - WATERPROOFING INSPECTION | Inspect - Check the waterproofing membrane for any damage or defects before installation. Record the batch number and expiry date of the membrane. | Not Started | Low |  |  | On-Site Checklist
Inspect - Membrane installation | ITP14 - WATERPROOFING INSPECTION | Inspect - Verify that the membrane is installed in strict accordance with the manufacturer's instructions and the project drawings. | Not Started | Low |  |  | On-Site Checklist
Inspect - Membrane overlaps | ITP14 - WATERPROOFING INSPECTION | Inspect - Ensure that the membrane overlaps are of the correct width (as specified by the manufacturer) and are properly sealed. | Not Started | Low |  |  | On-Site Checklist
Inspect - Corners and junctions | ITP14 - WATERPROOFING INSPECTION | Inspect - Confirm that all internal corners and junctions are correctly waterproofed with reinforcing tape or fabric as per the manufacturer's instructions. | Not Started | Low |  |  | On-Site Checklist
Inspect - Membrane surface | ITP14 - WATERPROOFING INSPECTION | Inspect - Inspect the membrane for any pinholes, tears, or other damage after installation. Pay close attention to areas around penetrations and corners. | Not Started | Low |  |  | On-Site Checklist
Test: Wet film thickness | ITP14 - WATERPROOFING INSPECTION | Test: Use a wet film thickness gauge to measure the wet film thickness of the membrane during application. Record the readings at multiple locations to ensure adequate coverage. | Not Started | Low |  |  | On-Site Checklist
Record - Coats and drying | ITP14 - WATERPROOFING INSPECTION | Record - Note the number of coats applied and the drying time between coats. | Not Started | Low |  |  | On-Site Checklist
Inspect - Final thickness compliance with AS 3740 and the manufacturer's specs | ITP14 - WATERPROOFING INSPECTION | Inspect - Ensure that the final membrane thickness meets the requirements of AS 3740 and the manufacturer's specifications. | Not Started | Low |  |  | On-Site Checklist
Inspect - Penetration seals | ITP14 - WATERPROOFING INSPECTION | Inspect - Verify that all penetrations (pipes, drains, floor wastes, etc.) are correctly sealed with appropriate waterproofing accessories (e.g., pipe collars, floor wastes) in accordance with the manufacturer's instructions. | Not Started | Low |  |  | On-Site Checklist
Inspect - Bond breakers | ITP14 - WATERPROOFING INSPECTION | Inspect - Ensure that the waterproofing membrane is seamlessly integrated with the penetration seals to provide a continuous waterproof barrier. | Not Started | Low |  |  | On-Site Checklist
Record - Bond breaker details | ITP14 - WATERPROOFING INSPECTION | nspect: Verify that bond breakers (e.g., foam strips, sealant) are correctly installed at all junctions between the waterproofing membrane and dissimilar materials (e.g., door frames, window sills) to prevent cracking and movement. | Not Started | Low |  |  | On-Site Checklist
Record - Site conditions | ITP14 - WATERPROOFING INSPECTION | Record - Note the type and location of bond breakers used. | Not Started | Low |  |  | On-Site Checklist
Test: Flood test | ITP14 - WATERPROOFING INSPECTION | Record - Note the ambient temperature and humidity during the inspection. Ensure these conditions are within the acceptable range for the membrane application. | Not Started | Low |  |  | On-Site Checklist
Inspect - Leakage signs | ITP14 - WATERPROOFING INSPECTION | Test: Conduct a water ponding test for a minimum of 24 hours (or as specified in AS 3740) to verify the integrity of the waterproofing system. Fill the wet area with water to a depth of at least 50mm. | Not Started | Low |  |  | On-Site Checklist
Record - Flood test results | ITP14 - WATERPROOFING INSPECTION | Inspect - Inspect for any signs of leakage or water penetration during and after the test. Pay close attention to areas around penetrations and corners. | Not Started | Low |  |  | On-Site Checklist
Record - Document test duration and observations. | ITP14 - WATERPROOFING INSPECTION | Record - Document the duration of the flood test and any observations. | Not Started | Low |  |  | On-Site Checklist
Inspect - Drying before trades | ITP14 - WATERPROOFING INSPECTION | Inspect - Allow the waterproofing membrane to dry completely before proceeding with subsequent trades (e.g., tiling). | Not Started | Low |  |  | On-Site Checklist
Record - Drying details | ITP14 - WATERPROOFING INSPECTION | Record - Note the drying time and conditions. | Not Started | Low |  |  | On-Site Checklist
Acknowledgement: Inspector confirmation of completed inspection accuracy and acceptance of responsibility | ITP14 - WATERPROOFING INSPECTION | Acknowledgement: I confirm that I have personally inspected every item on this checklist, all checks are accurate, and any issues have been addressed. I take full responsibility for the quality of this inspection. | Not Started | Low |  |  | On-Site Checklist
ITP11 - MECHANICAL SERVICES ROUGH-IN INSPECTION |  |  | Not Started | Low |  |  | On-Site Checklist
Inspect - Installation and compliance | ITP11 - MECHANICAL SERVICES ROUGH-IN INSPECTION | Inspect - All ductwork, vents, and HVAC equipment are installed correctly and meet specifications. | Not Started | Low |  |  | On-Site Checklist
Inspect - Duct sealing | ITP11 - MECHANICAL SERVICES ROUGH-IN INSPECTION | Inspect - Ductwork is properly sealed to prevent air leakage. | Not Started | Low |  |  | On-Site Checklist
Inspect - Duct insulation | ITP11 - MECHANICAL SERVICES ROUGH-IN INSPECTION | Inspect - Ductwork is insulated to prevent condensation and heat loss/gain. | Not Started | Low |  |  | On-Site Checklist
Inspect - Duct layout | ITP11 - MECHANICAL SERVICES ROUGH-IN INSPECTION | Inspect - Duct runs are as short as possible and not tangled up in the ceiling space. | Not Started | Low |  |  | On-Site Checklist
Inspect - Exhaust ventilation | ITP11 - MECHANICAL SERVICES ROUGH-IN INSPECTION | Inspect - All fan ducts are vented outside of the roof space. | Not Started | Low |  |  | On-Site Checklist
Inspect - Vent placement | ITP11 - MECHANICAL SERVICES ROUGH-IN INSPECTION | Inspect - Vents are located correctly and are free from obstructions. | Not Started | Low |  |  | On-Site Checklist
Inspect - HVAC Equipment installation | ITP11 - MECHANICAL SERVICES ROUGH-IN INSPECTION | Inspect - HVAC equipment is installed securely and has adequate clearance for maintenance. | Not Started | Low |  |  | On-Site Checklist
Acknowledgement: Inspector confirmation of completed inspection accuracy and acceptance of responsibility | ITP11 - MECHANICAL SERVICES ROUGH-IN INSPECTION | Acknowledgement: I confirm that I have personally inspected every item on this checklist, all checks are accurate, and any issues have been addressed. I take full responsibility for the quality of this inspection. | Not Started | Low |  |  | On-Site Checklist
ITP15 - MECHANICAL COMMISSIONING and INSPECTION |  |  | Not Started | Low |  |  | On-Site Checklist
Inspect - HVAC component installation | ITP15 - MECHANICAL COMMISSIONING and INSPECTION | Inspect - All HVAC system components (e.g., heating unit, cooling unit, thermostats) are installed correctly and in accordance with manufacturer's specifications and relevant Australian Standards. | Not Started | Low |  |  | On-Site Checklist
Inspect - Refrigerant pipework | ITP15 - MECHANICAL COMMISSIONING and INSPECTION | Inspect - Refrigerant pipework is installed correctly and is free from leaks. | Not Started | Low |  |  | On-Site Checklist
Inspect - Electrical connections | ITP15 - MECHANICAL COMMISSIONING and INSPECTION | Inspect - Electrical connections are secure and properly insulated. | Not Started | Low |  |  | On-Site Checklist
Inspect - Condensate drains | ITP15 - MECHANICAL COMMISSIONING and INSPECTION | Inspect - Condensate drains are installed correctly and are free from leaks. | Not Started | Low |  |  | On-Site Checklist
Test: Heating system | ITP15 - MECHANICAL COMMISSIONING and INSPECTION | Test: Operate the heating system and verify that it heats all zones to the desired temperature. | Not Started | Low |  |  | On-Site Checklist
Test: Cooling system | ITP15 - MECHANICAL COMMISSIONING and INSPECTION | Test: Operate the cooling system and verify that it cools all zones to the desired temperature. | Not Started | Low |  |  | On-Site Checklist
Test: Thermostat control | ITP15 - MECHANICAL COMMISSIONING and INSPECTION | Test: Check that the thermostat controls the system correctly and maintains the desired temperature. | Not Started | Low |  |  | On-Site Checklist
Test: Air filters | ITP15 - MECHANICAL COMMISSIONING and INSPECTION | Test: Verify that the air filters are clean and installed correctly. | Not Started | Low |  |  | On-Site Checklist
Test: Safety devices | ITP15 - MECHANICAL COMMISSIONING and INSPECTION | Test: Check that all safety devices (e.g., high-limit switches, pressure relief valves) are functioning correctly. | Not Started | Low |  |  | On-Site Checklist
Test: Airflow balance | ITP15 - MECHANICAL COMMISSIONING and INSPECTION | Test: Measure and adjust the airflow in each room/zone to ensure balanced heating and cooling throughout the building. | Not Started | Low |  |  | On-Site Checklist
Test: Refrigerant charge | ITP15 - MECHANICAL COMMISSIONING and INSPECTION | Test: If applicable, check the refrigerant charge in the system to ensure it is at the correct level. | Not Started | Low |  |  | On-Site Checklist
Inspect - Commissioning documentation | ITP15 - MECHANICAL COMMISSIONING and INSPECTION | Inspect - The HVAC installer has provided all necessary commissioning and testing documentation, including any warranty information. | Not Started | Low |  |  | On-Site Checklist
Record - Commissioning report | ITP15 - MECHANICAL COMMISSIONING and INSPECTION | Record - A detailed commissioning report should be completed, outlining the tests performed, results obtained, and any adjustments made to the system. | Not Started | Low |  |  | On-Site Checklist
Acknowledgement: Inspector confirmation of completed inspection accuracy and acceptance of responsibility | ITP15 - MECHANICAL COMMISSIONING and INSPECTION | Acknowledgement: I confirm that I have personally inspected every item on this checklist, all checks are accurate, and any issues have been addressed. I take full responsibility for the quality of this inspection. | Not Started | Low |  |  | On-Site Checklist
ITP18 - PLUMBING SERVICES ROUGH-IN INSPECTION |  |  | Not Started | Low |  |  | On-Site Checklist
Inspect - Plumbing installation | ITP18 - PLUMBING SERVICES ROUGH-IN INSPECTION | Inspect - All plumbing pipes and fixtures are installed correctly and meet code requirements. | Not Started | Low |  |  | On-Site Checklist
Inspect - Pipework support | ITP18 - PLUMBING SERVICES ROUGH-IN INSPECTION | Inspect - Pipework is adequately supported and secured. | Not Started | Low |  |  | On-Site Checklist
Inspect - Materials | ITP18 - PLUMBING SERVICES ROUGH-IN INSPECTION | Inspect - Correct materials are used for different applications (e.g., hot water, cold water, drainage). | Not Started | Low |  |  | On-Site Checklist
Inspect - Plumbing connections | ITP18 - PLUMBING SERVICES ROUGH-IN INSPECTION | Inspect - All connections are secure and watertight. | Not Started | Low |  |  | On-Site Checklist
Inspect - Drainage falls | ITP18 - PLUMBING SERVICES ROUGH-IN INSPECTION | Inspect - Drainage pipes have the correct fall and are free from obstructions. | Not Started | Low |  |  | On-Site Checklist
Inspect - Venting | ITP18 - PLUMBING SERVICES ROUGH-IN INSPECTION | Inspect - Venting is installed correctly to prevent sewer gases from entering the building. | Not Started | Low |  |  | On-Site Checklist
Test: Pressure test | ITP18 - PLUMBING SERVICES ROUGH-IN INSPECTION | Test: Conduct a pressure test to verify the integrity of the plumbing system. | Not Started | Low |  |  | On-Site Checklist
Inspect - Gas installation | ITP18 - PLUMBING SERVICES ROUGH-IN INSPECTION | Inspect - All gas pipes and fittings are installed correctly and meet gas code requirements. | Not Started | Low |  |  | On-Site Checklist
Inspect - Gas pipework support | ITP18 - PLUMBING SERVICES ROUGH-IN INSPECTION | Inspect - Gas pipework is adequately supported and secured. | Not Started | Low |  |  | On-Site Checklist
Inspect - Gas materials | ITP18 - PLUMBING SERVICES ROUGH-IN INSPECTION | Inspect - Correct materials are used for gas installations. | Not Started | Low |  |  | On-Site Checklist
Inspect - Gas connections | ITP18 - PLUMBING SERVICES ROUGH-IN INSPECTION | Inspect - All connections are secure and gas-tight. | Not Started | Low |  |  | On-Site Checklist
Inspect - Gas appliances | ITP18 - PLUMBING SERVICES ROUGH-IN INSPECTION | Inspect - Gas appliances are installed correctly and have adequate ventilation. | Not Started | Low |  |  | On-Site Checklist
Acknowledgement: Inspector confirmation of completed inspection accuracy and acceptance of responsibility | ITP18 - PLUMBING SERVICES ROUGH-IN INSPECTION | Acknowledgement: I confirm that I have personally inspected every item on this checklist, all checks are accurate, and any issues have been addressed. I take full responsibility for the quality of this inspection. | Not Started | Low |  |  | On-Site Checklist
ITP17 - PLUMBING FINAL INSPECTION |  |  | Not Started | Low |  |  | On-Site Checklist
Test: Water flow | ITP17 - PLUMBING FINAL INSPECTION | Test: Turn on all taps (hot and cold) to check for adequate water flow and pressure. | Not Started | Low |  |  | On-Site Checklist
Inspect - Water pressure | ITP17 - PLUMBING FINAL INSPECTION | Inspect - Water pressure at all outlets is within the acceptable range. | Not Started | Low |  |  | On-Site Checklist
Inspect - Fixture installation | ITP17 - PLUMBING FINAL INSPECTION | Inspect - All fixtures (taps, showers, toilets, etc.) are installed correctly and operate smoothly. | Not Started | Low |  |  | On-Site Checklist
Inspect - Fixture quality | ITP17 - PLUMBING FINAL INSPECTION | Inspect - All plumbing fittings and fixtures are straight, aligned, symmetrical to surroundings and free from defects. | Not Started | Low |  |  | On-Site Checklist
Inspect - Water leaks | ITP17 - PLUMBING FINAL INSPECTION | Inspect - No leaks are present in any of the water supply pipes or fixtures. | Not Started | Low |  |  | On-Site Checklist
Test: Drainage | ITP17 - PLUMBING FINAL INSPECTION | Test: Flush all toilets and run water in sinks and basins to check for proper drainage. | Not Started | Low |  |  | On-Site Checklist
Inspect - Drainage leaks | ITP17 - PLUMBING FINAL INSPECTION | Inspect - No leaks are present in any of the drainage pipes or fixtures. | Not Started | Low |  |  | On-Site Checklist
Test: Hot water system | ITP17 - PLUMBING FINAL INSPECTION | Test: Check that the hot water system is operating correctly and provides hot water at the correct temperature at all outlets. | Not Started | Low |  |  | On-Site Checklist
Inspect - TPR valve | ITP17 - PLUMBING FINAL INSPECTION | Inspect - The temperature and pressure relief valve is installed and functioning correctly. | Not Started | Low |  |  | On-Site Checklist
Test: Additional plumbing components | ITP17 - PLUMBING FINAL INSPECTION | Test: If applicable, test any other plumbing components (e.g., rainwater tanks, pumps, filters) to ensure they are functioning as intended. | Not Started | Low |  |  | On-Site Checklist
Inspect - Compliance certificate | ITP17 - PLUMBING FINAL INSPECTION | Inspect - The plumber has provided a Plumbing and Drainage Certificate (Compliance Certificate) as required by the PCA. | Not Started | Low |  |  | On-Site Checklist
Acknowledgement: Inspector confirmation of completed inspection accuracy and acceptance of responsibility | ITP17 - PLUMBING FINAL INSPECTION | Acknowledgement: I confirm that I have personally inspected every item on this checklist, all checks are accurate, and any issues have been addressed. I take full responsibility for the quality of this inspection. | Not Started | Low |  |  | On-Site Checklist
ITP16 - GAS INSTALLATION INSPECTION |  |  | Not Started | Low |  |  | On-Site Checklist
Inspect - Gas appliances | ITP16 - GAS INSTALLATION INSPECTION | Inspect - All gas appliances (e.g., stove, oven, hot water system, heater) are installed correctly and meet the manufacturer's specifications and relevant Australian Standards. | Not Started | Low |  |  | On-Site Checklist
Inspect - Ventilation | ITP16 - GAS INSTALLATION INSPECTION | Inspect - Gas appliances have adequate ventilation to prevent the buildup of harmful gases. | Not Started | Low |  |  | On-Site Checklist
Inspect - Flue installation | ITP16 - GAS INSTALLATION INSPECTION | Inspect - Flue pipes are installed correctly and terminate safely outside the building. | Not Started | Low |  |  | On-Site Checklist
Test: Appliance operation | ITP16 - GAS INSTALLATION INSPECTION | Test: Operate each gas appliance to ensure it is functioning correctly and safely. | Not Started | Low |  |  | On-Site Checklist
Inspect - Gas safety devices | ITP16 - GAS INSTALLATION INSPECTION | Inspect - All necessary gas safety devices (e.g., gas isolation valves, flame failure devices) are installed and functioning correctly. | Not Started | Low |  |  | On-Site Checklist
Test: Gas pressure | ITP16 - GAS INSTALLATION INSPECTION | Test: Conduct a gas pressure test to verify the integrity of the gas pipework system. | Not Started | Low |  |  | On-Site Checklist
Test: Gas leaks | ITP16 - GAS INSTALLATION INSPECTION | Test: Conduct a gas leak test using an approved gas detector to ensure no gas leaks are present. | Not Started | Low |  |  | On-Site Checklist
Inspect - Compliance certificate | ITP16 - GAS INSTALLATION INSPECTION | Inspect - A licensed gas fitter has provided a Gas Certificate of Compliance as required by AS/NZS 5601. | Not Started | Low |  |  | On-Site Checklist
Acknowledgement: Inspector confirmation of completed inspection accuracy and acceptance of responsibility | ITP16 - GAS INSTALLATION INSPECTION | Acknowledgement: I confirm that I have personally inspected every item on this checklist, all checks are accurate, and any issues have been addressed. I take full responsibility for the quality of this inspection. | Not Started | Low |  |  | On-Site Checklist
ITP20 - ELECTRICAL SERVICES ROUGH-IN INSPECTION |  |  | Not Started | Low |  |  | On-Site Checklist
Inspect - Electrical installation | ITP20 - ELECTRICAL SERVICES ROUGH-IN INSPECTION | Inspect - All electrical wiring, outlets, and switches are installed correctly and meet code requirements. | Not Started | Low |  |  | On-Site Checklist
Inspect - Wiring size and protection | ITP20 - ELECTRICAL SERVICES ROUGH-IN INSPECTION | Inspect - Wiring is correctly sized and protected by appropriate circuit breakers. | Not Started | Low |  |  | On-Site Checklist
Inspect - Electrical connections | ITP20 - ELECTRICAL SERVICES ROUGH-IN INSPECTION | Inspect - All connections are secure and properly insulated. | Not Started | Low |  |  | On-Site Checklist
Inspect - Earthing | ITP20 - ELECTRICAL SERVICES ROUGH-IN INSPECTION | Inspect - Earthing (grounding) is installed correctly. | Not Started | Low |  |  | On-Site Checklist
Inspect - Labeling | ITP20 - ELECTRICAL SERVICES ROUGH-IN INSPECTION | Inspect - All electrical components are properly labeled. | Not Started | Low |  |  | On-Site Checklist
Inspect - Cable support | ITP20 - ELECTRICAL SERVICES ROUGH-IN INSPECTION | Inspect - All electrical cables passing through the interior lining have clear and secure brackets. | Not Started | Low |  |  | On-Site Checklist
Test: Insulation resistance | ITP20 - ELECTRICAL SERVICES ROUGH-IN INSPECTION | Test: Conduct an insulation resistance test to verify the safety of the electrical system. | Not Started | Low |  |  | On-Site Checklist
Inspect - Telecommunications cabling | ITP20 - ELECTRICAL SERVICES ROUGH-IN INSPECTION | Inspect - NBN/starlink/telecommunications cabling is installed correctly and meets provider requirements. | Not Started | Low |  |  | On-Site Checklist
Inspect - Telecommunications labeling | ITP20 - ELECTRICAL SERVICES ROUGH-IN INSPECTION | Inspect - NBN/starlink/telecommunications cabling is adequately labeled and terminated. | Not Started | Low |  |  | On-Site Checklist
Inspect - TV cabling | ITP20 - ELECTRICAL SERVICES ROUGH-IN INSPECTION | Inspect - TV antenna cabling is installed correctly and meets Australian standards. | Not Started | Low |  |  | On-Site Checklist
Inspect - TV cabling labeling | ITP20 - ELECTRICAL SERVICES ROUGH-IN INSPECTION | Inspect - Cabling is adequately labeled and terminated. | Not Started | Low |  |  | On-Site Checklist
Inspect - TV antenna | ITP20 - ELECTRICAL SERVICES ROUGH-IN INSPECTION | Inspect - TV antenna is installed correctly and is securely mounted. | Not Started | Low |  |  | On-Site Checklist
Inspect - Data cabling | ITP20 - ELECTRICAL SERVICES ROUGH-IN INSPECTION | Inspect - Data cabling (e.g., Ethernet, coaxial) is installed correctly and meets specifications. | Not Started | Low |  |  | On-Site Checklist
Inspect - Data cabling labeling | ITP20 - ELECTRICAL SERVICES ROUGH-IN INSPECTION | Inspect - Data cabling is adequately labeled and terminated. | Not Started | Low |  |  | On-Site Checklist
Inspect - Data outlets | ITP20 - ELECTRICAL SERVICES ROUGH-IN INSPECTION | Inspect - Data outlets are installed in the correct locations. | Not Started | Low |  |  | On-Site Checklist
Inspect - Security system installation | ITP20 - ELECTRICAL SERVICES ROUGH-IN INSPECTION | Inspect - Security system components (e.g., sensors, control panel, alarm) are installed correctly and meet relevant standards. | Not Started | Low |  |  | On-Site Checklist
Inspect - Security wiring | ITP20 - ELECTRICAL SERVICES ROUGH-IN INSPECTION | Inspect - Security system wiring and connections are secure and properly concealed. | Not Started | Low |  |  | On-Site Checklist
Inspect - Security testing | ITP20 - ELECTRICAL SERVICES ROUGH-IN INSPECTION | Inspect - Security system is functional and tested. | Not Started | Low |  |  | On-Site Checklist
Inspect - Other services | ITP20 - ELECTRICAL SERVICES ROUGH-IN INSPECTION | Inspect - Any other services (e.g., home automation, intercom) are installed correctly and meet relevant standards and specifications. | Not Started | Low |  |  | On-Site Checklist
Acknowledgement: Inspector confirmation of completed inspection accuracy and acceptance of responsibility | ITP20 - ELECTRICAL SERVICES ROUGH-IN INSPECTION | Acknowledgement: I confirm that I have personally inspected every item on this checklist, all checks are accurate, and any issues have been addressed. I take full responsibility for the quality of this inspection. | Not Started | Low |  |  | On-Site Checklist
ITP18 - ELECTRICAL FINAL INSPECTION |  |  | Not Started | Low |  |  | On-Site Checklist
Inspect - Wiring rules compliance | ITP18 - ELECTRICAL FINAL INSPECTION | Inspect - All electrical installations comply with AS/NZS 3000 Electrical Installations ("Wiring Rules"). | Not Started | Low |  |  | On-Site Checklist
Inspect - Circuit protection | ITP18 - ELECTRICAL FINAL INSPECTION | Inspect - All circuits are correctly protected by the appropriate circuit breakers or fuses. | Not Started | Low |  |  | On-Site Checklist
Inspect - RCDs | ITP18 - ELECTRICAL FINAL INSPECTION | Inspect - Residual Current Devices (RCDs) are installed and functioning correctly. | Not Started | Low |  |  | On-Site Checklist
Inspect - Earthing system | ITP18 - ELECTRICAL FINAL INSPECTION | Inspect - Earthing (grounding) system is installed correctly. | Not Started | Low |  |  | On-Site Checklist
Inspect - Appliance installation | ITP18 - ELECTRICAL FINAL INSPECTION | Inspect - All electrical equipment and appliances are safely installed and earthed. | Not Started | Low |  |  | On-Site Checklist
Inspect - Switchboard installation | ITP18 - ELECTRICAL FINAL INSPECTION | Inspect - The switchboard is installed correctly and is accessible. | Not Started | Low |  |  | On-Site Checklist
Inspect - Circuit labeling | ITP18 - ELECTRICAL FINAL INSPECTION | Inspect - All circuits are clearly labeled in the switchboard. | Not Started | Low |  |  | On-Site Checklist
Inspect - Light fittings | ITP18 - ELECTRICAL FINAL INSPECTION | Inspect - All light fittings are installed correctly, functioning and are straight, aligned, symmetrical to surroundings and free from defects. | Not Started | Low |  |  | On-Site Checklist
Inspect - Light switches | ITP18 - ELECTRICAL FINAL INSPECTION | Inspect - Light switches operate correctly. | Not Started | Low |  |  | On-Site Checklist
Inspect - Power outlets | ITP18 - ELECTRICAL FINAL INSPECTION | Inspect - All power outlets are installed correctly and are functioning. | Not Started | Low |  |  | On-Site Checklist
Inspect - Power outlet locations | ITP18 - ELECTRICAL FINAL INSPECTION | Inspect - Power outlets are located in accordance with AS/NZS 3000. | Not Started | Low |  |  | On-Site Checklist
Inspect - Weatherproof outlets | ITP18 - ELECTRICAL FINAL INSPECTION | Inspect - Weatherproof outlets are installed in external areas. | Not Started | Low |  |  | On-Site Checklist
Inspect - Electrical equipment | ITP18 - ELECTRICAL FINAL INSPECTION | Inspect - All other electrical equipment (e.g., exhaust fans, range hoods) is installed correctly and is functioning. | Not Started | Low |  |  | On-Site Checklist
Inspect - Electrical certificate | ITP18 - ELECTRICAL FINAL INSPECTION | Inspect - The electrician has provided an Electrical Certificate of Compliance. | Not Started | Low |  |  | On-Site Checklist
Inspect - Smoke alarm locations | ITP18 - ELECTRICAL FINAL INSPECTION | Inspect - Smoke alarms are installed in all required locations according to AS 3786 | Not Started | Low |  |  | On-Site Checklist
Inspect - Smoke alarm type | ITP18 - ELECTRICAL FINAL INSPECTION | Inspect - Smoke alarms are of the correct type (photoelectric, ionization, or a combination) and meet Australian Standards (AS 3786). | Not Started | Low |  |  | On-Site Checklist
Inspect - Smoke alarm interconnection | ITP18 - ELECTRICAL FINAL INSPECTION | Inspect - Smoke alarms are interconnected, so that if one alarm activates, all alarms in the building sound. | Not Started | Low |  |  | On-Site Checklist
Test: Smoke alarms | ITP18 - ELECTRICAL FINAL INSPECTION | Test: All smoke alarms to ensure they are functioning correctly. | Not Started | Low |  |  | On-Site Checklist
Inspect - Smoke alarm power supply | ITP18 - ELECTRICAL FINAL INSPECTION | Inspect - Smoke alarms are hardwired to the mains power supply with a backup battery. | Not Started | Low |  |  | On-Site Checklist
Acknowledgement: Inspector confirmation of completed inspection accuracy and acceptance of responsibility | ITP18 - ELECTRICAL FINAL INSPECTION | Acknowledgement: I confirm that I have personally inspected every item on this checklist, all checks are accurate, and any issues have been addressed. I take full responsibility for the quality of this inspection. | Not Started | Low |  |  | On-Site Checklist
ITP02 - FINAL INSPECTION |  |  | Not Started | Low |  |  | On-Site Checklist
Inspect - Compliance | ITP02 - FINAL INSPECTION | Inspect - Verify that all work complies with the approved drawings, specifications, and all relevant building codes and Australian Standards. | Not Started | Low |  |  | On-Site Checklist
Inspect - Variations | ITP02 - FINAL INSPECTION | Inspect - Confirm that all variations to the original plans are documented and approved. | Not Started | Low |  |  | On-Site Checklist
Inspect - External elements | ITP02 - FINAL INSPECTION | Inspect - Check all external elements (cladding, roofing, windows, doors) for proper installation, weather tightness, and compliance with specifications. | Not Started | Low |  |  | On-Site Checklist
Inspect - Sealant joints | ITP02 - FINAL INSPECTION | Inspect - Confirm that all sealant joints are neat, tidy, and provide an effective seal. | Not Started | Low |  |  | On-Site Checklist
Inspect - Gutters and downpipes | ITP02 - FINAL INSPECTION | Inspect - Verify that gutters and downpipes are installed correctly and are free from leaks. | Not Started | Low |  |  | On-Site Checklist
Test: Airtightness | ITP02 - FINAL INSPECTION | Test: Conduct a final blower door test to measure the airtightness of the building envelope. Record the building volume, airflow rate at 50 Pa, and calculated ACH50. Compare the results to the project target or building code requirements. If necessary, identify and document any major air leakage pathways. | Not Started | Low |  |  | On-Site Checklist
Inspect - Internal finishes | ITP02 - FINAL INSPECTION | Inspect - Check all internal walls, ceilings, and floors for a high-quality finish, free from defects (e.g., cracks, uneven surfaces, damage). | Not Started | Low |  |  | On-Site Checklist
Inspect - Paintwork | ITP02 - FINAL INSPECTION | Inspect - Confirm that all paintwork is complete and to a high standard, with no visible imperfections. | Not Started | Low |  |  | On-Site Checklist
Inspect - Tiling | ITP02 - FINAL INSPECTION | Inspect - Verify that all tiles are installed correctly, with even grout lines and no cracked or chipped tiles. | Not Started | Low |  |  | On-Site Checklist
Inspect - Flooring | ITP02 - FINAL INSPECTION | Inspect - Check that all flooring (carpet, timber, vinyl) is installed correctly and is free from damage. | Not Started | Low |  |  | On-Site Checklist
Inspect - Electrical fixtures | ITP02 - FINAL INSPECTION | Inspect - Confirm that all light fittings, power points, switches, and other electrical fixtures are installed correctly and are functional. | Not Started | Low |  |  | On-Site Checklist
Inspect - Plumbing fixtures | ITP02 - FINAL INSPECTION | Inspect - Confirm that all plumbing fixtures (taps, showers, toilets, sinks) are installed correctly and are free from leaks. | Not Started | Low |  |  | On-Site Checklist
Test: Plumbing systems | ITP02 - FINAL INSPECTION | Test: Test all plumbing systems (hot and cold water, drainage) to ensure they are functioning correctly and are free from leaks. | Not Started | Low |  |  | On-Site Checklist
Test: Electrical systems | ITP02 - FINAL INSPECTION | Test: Test all electrical systems (lights, power points, appliances) to ensure they are functioning correctly and are safe. | Not Started | Low |  |  | On-Site Checklist
Test: HVAC system | ITP02 - FINAL INSPECTION | Test: Test the HVAC system (heating and cooling) to ensure it is functioning correctly and meets the specified performance requirements. | Not Started | Low |  |  | On-Site Checklist
Inspect - Smoke alarms | ITP02 - FINAL INSPECTION | Inspect - Confirm that all smoke alarms are installed correctly and are functional. | Not Started | Low |  |  | On-Site Checklist
Inspect - Safety features | ITP02 - FINAL INSPECTION | Inspect - Verify that all required safety features (e.g., handrails, balustrades) are installed and meet safety standards. | Not Started | Low |  |  | On-Site Checklist
Inspect - External works | ITP02 - FINAL INSPECTION | Inspect - Check that all external works (e.g., paving, landscaping, fencing) are complete and meet the required standards. | Not Started | Low |  |  | On-Site Checklist
Inspect - Documentation | ITP02 - FINAL INSPECTION | Inspect - Confirm that all required certificates and documentation are complete and available, including: Occupancy Certificate (or Certificate of Occupancy) Plumbing and Drainage Certificate Electrical Certificate of Compliance Gas Certificate of Compliance Energy Efficiency Certificates (if applicable) Other relevant certificates (e.g., Bushfire, Acoustic) | Not Started | Low |  |  | On-Site Checklist
Inspect - Manuals and warranties | ITP02 - FINAL INSPECTION | Inspect - Verify that all appliance manuals, warranty information, and maintenance instructions are compiled and provided to the client. | Not Started | Low |  |  | On-Site Checklist
Acknowledgement: Inspector confirmatio of building work completion and compliance | ITP02 - FINAL INSPECTION | Acknowledgement: I confirm compliance with form 71A and Confirm (a) all building work is complete; and (b) all directions given under the Building Act 2016 and Building Regulations 2016 have been complied with; and (c) the building work as constructed is in compliance with the National Construction Code, the approved plans, specifications and conditions of the Certificate of Likely Compliance (or a Building Permit) granted for the work | Not Started | Low |  |  | On-Site Checklist
Acknowledgement: Inspector confirmation of completed inspection accuracy and acceptance of responsibility | ITP02 - FINAL INSPECTION | Acknowledgement: I confirm that I have personally inspected every item on this checklist, all checks are accurate, and any issues have been addressed. I take full responsibility for the quality of this inspection. | Not Started | Low |  |  | On-Site Checklist
JC08 - JOINERY |  |  | Not Started | Low |  |  | Job Stage
Joinery Selected | JC08 - JOINERY |  | Not Started | Low |  |  | Job Stage
Handles ordered | JC08 - JOINERY |  | Not Started | Low
Joinery plans received | JC08 - JOINERY |  | Not Started | Low |  |  | Job Stage
Joinery plans approved by Project Manager | JC08 - JOINERY |  | Not Started | Low |  |  | Job Stage
Joinery deposit paid | JC08 - JOINERY |  | Not Started | Low |  |  | Job Stage
Joinery plans reviewed | JC08 - JOINERY |  | Not Started | Low |  |  | Job Stage
EST01 - ESTIMATE START MEETING |  | This checklist is used in the Awaiting to Start stage. Its purpose is to ensure all initial project setup, document organisation, preliminary information gathering, and key decisions (like outsourcing) are complete before starting the detailed contract estimate process. | Not Started | Low |  |  | Job Stage
01. All documents have been received from designer etc | EST01 - ESTIMATE START MEETING |  | Not Started | Low
02. All documents have been gathered for the meeting. | EST01 - ESTIMATE START MEETING |  | Not Started | Low
03. Job folder is set up in Google Drive | EST01 - ESTIMATE START MEETING |  | Not Started | Low
04. Job folder is set up in Buildern | EST01 - ESTIMATE START MEETING |  | Not Started | Low
05. All job files are organised and saved using the standard file folder structure. | EST01 - ESTIMATE START MEETING |  | Not Started | Low
06. No job files or sales-related information are left in email or saved on the desktop. | EST01 - ESTIMATE START MEETING |  | Not Started | Low
07. Create E-Notes Sheet | EST01 - ESTIMATE START MEETING |  | Not Started | Low
08. Create Labour Estimating Sheet | EST01 - ESTIMATE START MEETING |  | Not Started | Low
09. All required and current documents are listed in the document register. | EST01 - ESTIMATE START MEETING |  | Not Started | Low
10.3. Sweeping Review - A quick review of the project has been completed to get a general idea and identify unusual or new items. | EST01 - ESTIMATE START MEETING |  | Not Started | Low
11. A quick review of the specifications has been completed to get a general idea and identify unusual or new items. | EST01 - ESTIMATE START MEETING |  | Not Started | Low
12. All Requests for Information (questions for clarification) have been identified. | EST01 - ESTIMATE START MEETING |  | Not Started | Low
13. All Requests for Quote (requests for pricing) have been identified. | EST01 - ESTIMATE START MEETING |  | Not Started | Low
14. All necessary checkpoint meetings are booked in the calendar. | EST01 - ESTIMATE START MEETING |  | Not Started | Low
15. Documents required have been requested | EST01 - ESTIMATE START MEETING |  | Not Started | Low
16. Pricing is only done from approved construction documents, not from sketches or drafts. | EST01 - ESTIMATE START MEETING |  | Not Started | Low
17. It has been identified whether the estimate will be sent to an external company or completed by our team internally. | EST01 - ESTIMATE START MEETING |  | Not Started | Low
18. If sending the estimate to an external company, the company has been selected and confirmed. | EST01 - ESTIMATE START MEETING |  | Not Started | Low
19. A job start meeting has been conducted to review the basics of the plans. | EST01 - ESTIMATE START MEETING |  | Not Started | Low
20. Two people have reviewed the initial plans. | EST01 - ESTIMATE START MEETING |  | Not Started | Low
21. The invoice for the quote has been paid if it is a service we charge for. | EST01 - ESTIMATE START MEETING |  | Not Started | Low
22. If any part of the estimate is to be done by an external company, a Purchase Order has been sent to that company. | EST01 - ESTIMATE START MEETING |  | Not Started | Low
23. The price book has been confirmed as currently updated before the estimate starts. | EST01 - ESTIMATE START MEETING |  | Not Started | Low
24. If specifications are not provided by the client or architect, the specification sheet has been collected or created. | EST01 - ESTIMATE START MEETING |  | Not Started | Low
25. Final Action: I acknowledge that all items on this checklist have been completed. Move to the next phase and load the next checklist. | EST01 - ESTIMATE START MEETING |  | Not Started | Low
10.4. Select NO to all categories that are not required | EST01 - ESTIMATE START MEETING |  | Not Started | Low
24.5. Admin to create the estimate template in Buildern and adjust categories in Buildern to suit categories in E notes | EST01 - ESTIMATE START MEETING |  | Not Started | Low
10.1. Sweeping Review - From Details on page into E-notes | EST01 - ESTIMATE START MEETING |  | Not Started | Low
10.2. Sweeping Review - Through E-Notes Categories | EST01 - ESTIMATE START MEETING |  | Not Started | Low
EST02 - AWAITING DOCUMENTATION |  | This checklist is used in the Awaiting to Start stage. Its purpose is to confirm the receipt and proper filing of all official, approved, and detailed contract-level documentation (plans, engineering, specs, selections, consultant reports) for the project. | Not Started | Low |  |  | Job Stage
01. The approved architectural plans are available. | EST02 - AWAITING DOCUMENTATION |  | Not Started | Low |  |  | Job Stage
02. The approved engineering plans are available. | EST02 - AWAITING DOCUMENTATION |  | Not Started | Low |  |  | Job Stage
03. The approved specification document is available. | EST02 - AWAITING DOCUMENTATION |  | Not Started | Low |  |  | Job Stage
04. The approved selection schedule is available. | EST02 - AWAITING DOCUMENTATION |  | Not Started | Low |  |  | Job Stage
05. All product information and installation guides are available. | EST02 - AWAITING DOCUMENTATION |  | Not Started | Low |  |  | Job Stage
06. Any client-specific supplier information is documented. | EST02 - AWAITING DOCUMENTATION |  | Not Started | Low |  |  | Job Stage
07. All necessary consultant reports are available. | EST02 - AWAITING DOCUMENTATION |  | Not Started | Low |  |  | Job Stage
08. The CAD Files (DWGs of architectural plans) are available. | EST02 - AWAITING DOCUMENTATION |  | Not Started | Low |  |  | Job Stage
09. Survey Files / Contour Plans are available. | EST02 - AWAITING DOCUMENTATION |  | Not Started | Low |  |  | Job Stage
10. All documents have been received, uploaded to Buildern in the correct folder, and file names are formatted correctly. | EST02 - AWAITING DOCUMENTATION |  | Not Started | Low |  |  | Job Stage
11. The date all documents were received is recorded. | EST02 - AWAITING DOCUMENTATION |  | Not Started | Low |  |  | Job Stage
12.The document source is recorded. | EST02 - AWAITING DOCUMENTATION |  | Not Started | Low |  |  | Job Stage
13. The homeowner has been confirmed that all required documents have been received and the estimate process can now begin. The date the estimate will be completed has been provided. | EST02 - AWAITING DOCUMENTATION |  | Not Started | Low |  |  | Job Stage
14. Final Action: I acknowledge that all items on this checklist have been completed. Move to the next phase and load the next checklist. | EST02 - AWAITING DOCUMENTATION |  | Not Started | Low |  |  | Job Stage
EST03 - CATEGORY CHECKLIST MEETING |  |  | Not Started | Low |  |  | Job Stage
01. Conduct a meeting to review all categories in the job. | EST03 - CATEGORY CHECKLIST MEETING |  | Not Started | Low |  |  | Job Stage
02. Confirm what needs to be quoted for each category. | EST03 - CATEGORY CHECKLIST MEETING |  | Not Started | Low |  |  | Job Stage
03. Confirm what needs to be included in Requests for Information (RFIs) for each category. | EST03 - CATEGORY CHECKLIST MEETING |  | Not Started | Low |  |  | Job Stage
04. Confirm what needs to be included in Requests for Quote (RFQs) for each category. | EST03 - CATEGORY CHECKLIST MEETING |  | Not Started | Low |  |  | Job Stage
05. Final Action: I acknowledge that all items on this checklist have been completed. Move to the next phase and load the next checklist. | EST03 - CATEGORY CHECKLIST MEETING |  | Not Started | Low |  |  | Job Stage
EST04 - RFIS & RFQS ISSUED |  |  | Not Started | Low |  |  | Job Stage
01. All project documents (plans, specifications, etc.) have been read and processed. | EST04 - RFIS & RFQS ISSUED |  | Not Started | Low |  |  | Job Stage
02. Architectural documents have been reviewed, and detailed estimate notes have been written. | EST04 - RFIS & RFQS ISSUED |  | Not Started | Low |  |  | Job Stage
03. Engineering documents have been reviewed, and detailed estimate notes have been written. | EST04 - RFIS & RFQS ISSUED |  | Not Started | Low |  |  | Job Stage
04. Selection documents have been reviewed, and detailed estimate notes have been written. | EST04 - RFIS & RFQS ISSUED |  | Not Started | Low |  |  | Job Stage
05. Specification documents have been reviewed, and detailed estimate notes have been written. | EST04 - RFIS & RFQS ISSUED |  | Not Started | Low |  |  | Job Stage
06. A detailed list of questions for clarification (RFIs) has been created. | EST04 - RFIS & RFQS ISSUED |  | Not Started | Low |  |  | Job Stage
07. All questions for clarification (RFIs) have been sent to the architect or client. | EST04 - RFIS & RFQS ISSUED |  | Not Started | Low |  |  | Job Stage
08. All pricing request packages for subcontractors have been prepared. | EST04 - RFIS & RFQS ISSUED |  | Not Started | Low |  |  | Job Stage
09. All pricing request packages have been sent to subcontractors with clear due dates. | EST04 - RFIS & RFQS ISSUED |  | Not Started | Low |  |  | Job Stage
10. A formal request letter has been used for all pricing requests. | EST04 - RFIS & RFQS ISSUED |  | Not Started | Low |  |  | Job Stage
11. Clear deadlines for all pricing submissions have been set. | EST04 - RFIS & RFQS ISSUED |  | Not Started | Low |  |  | Job Stage
12. Calendar invitations for pricing submission deadlines have been sent. | EST04 - RFIS & RFQS ISSUED |  | Not Started | Low |  |  | Job Stage
13. Supplier pricing for specific products and materials has been requested. | EST04 - RFIS & RFQS ISSUED |  | Not Started | Low |  |  | Job Stage
14. Prices in the price book are up to date. | EST04 - RFIS & RFQS ISSUED |  | Not Started | Low |  |  | Job Stage
15. The decision has been made if the material quantity take-off or the entire estimate will be done by our team or by an external company. | EST04 - RFIS & RFQS ISSUED |  | Not Started | Low |  |  | Job Stage
16. Plans have been uploaded to Wunderbuild and set up for measuring quantities (take-offs). | EST04 - RFIS & RFQS ISSUED |  | Not Started | Low |  |  | Job Stage
17. A log of all questions for clarification (RFIs) that were sent out is kept for record-keeping. | EST04 - RFIS & RFQS ISSUED |  | Not Started | Low |  |  | Job Stage
18. If sending the estimate to an external company: The complete project document package has been prepared and sent to the external estimating company. | EST04 - RFIS & RFQS ISSUED |  | Not Started | Low |  |  | Job Stage
19. If sending the estimate to an external company: The external estimating company has confirmed receipt of the documents. | EST04 - RFIS & RFQS ISSUED |  | Not Started | Low |  |  | Job Stage
20. If sending the estimate to an external company: Clear communication rules and deadlines have been set up with the external estimating company. | EST04 - RFIS & RFQS ISSUED |  | Not Started | Low |  |  | Job Stage
21. All relevant meetings with the client and architect throughout the project have been booked. | EST04 - RFIS & RFQS ISSUED |  | Not Started | Low |  |  | Job Stage
22. Final Action: I acknowledge that all items on this checklist have been completed. Move to the next phase and load the next checklist. | EST04 - RFIS & RFQS ISSUED |  | Not Started | Low |  |  | Job Stage
EST05 - ESTIMATE COMPILATION |  |  | Not Started | Low |  |  | Job Stage
01. A detailed count of materials (bill of quantities and take-offs), including measuring from plans, has been performed. | EST05 - ESTIMATE COMPILATION |  | Not Started | Low |  |  | Job Stage
02. Labour costs have been calculated using the labour cost calculator, and each labour category has been checked off. | EST05 - ESTIMATE COMPILATION |  | Not Started | Low |  |  | Job Stage
03. Quotes from subcontractors have been received. | EST05 - ESTIMATE COMPILATION |  | Not Started | Low |  |  | Job Stage
04. A record of all pricing responses and different versions is kept using a quote register. | EST05 - ESTIMATE COMPILATION |  | Not Started | Low |  |  | Job Stage
05. A log of all responses to questions for clarification (RFIs) is kept for record-keeping. | EST05 - ESTIMATE COMPILATION |  | Not Started | Low |  |  | Job Stage
06. All parts of the estimate have been put together into one complete estimate. | EST05 - ESTIMATE COMPILATION |  | Not Started | Low |  |  | Job Stage
07. The estimate has been updated if anything changes or if there are responses to questions for clarification (RFIs). | EST05 - ESTIMATE COMPILATION |  | Not Started | Low |  |  | Job Stage
08. Final Action: I acknowledge that all items on this checklist have been completed. Move to the next phase and load the next checklist. | EST05 - ESTIMATE COMPILATION |  | Not Started | Low |  |  | Job Stage
EST06 - OUTSOURCED ESTIMATE RECEIPT & REVIEW |  |  | Not Started | Low |  |  | Job Stage
01. The complete detailed estimate has been received from the external estimating company. | EST06 - OUTSOURCED ESTIMATE RECEIPT & REVIEW |  | Not Started | Low |  |  | Job Stage
02. An initial review of the external estimate has been done to make sure it is complete (e.g., all trades are covered, all quantities are provided). | EST06 - OUTSOURCED ESTIMATE RECEIPT & REVIEW |  | Not Started | Low |  |  | Job Stage
03. All responses to questions for clarification (RFIs) have been confirmed as included by the external estimator. | EST06 - OUTSOURCED ESTIMATE RECEIPT & REVIEW |  | Not Started | Low |  |  | Job Stage
04. All responses to pricing requests (RFQs) have been confirmed as included by the external estimator. | EST06 - OUTSOURCED ESTIMATE RECEIPT & REVIEW |  | Not Started | Low |  |  | Job Stage
05. Any specific notes or assumptions made by the external estimator have been checked. | EST06 - OUTSOURCED ESTIMATE RECEIPT & REVIEW |  | Not Started | Low |  |  | Job Stage
06. Final Action: I acknowledge that all items on this checklist have been completed. Move to the next phase and load the next checklist. | EST06 - OUTSOURCED ESTIMATE RECEIPT & REVIEW |  | Not Started | Low |  |  | Job Stage
EST07 - QUALITY CONTROL & PROFITABILITY CHECKS |  |  | Not Started | Low |  |  | Job Stage
01. Subcontractor quotes have been reviewed for completeness, how competitive they are, and if they follow project rules. | EST07 - QUALITY CONTROL & PROFITABILITY CHECKS |  | Not Started | Low |  |  | Job Stage
02. A 25% buffer has been added to framing material counts. | EST07 - QUALITY CONTROL & PROFITABILITY CHECKS |  | Not Started | Low |  |  | Job Stage
03. A 10–25% buffer has been added to concrete and topping material counts. | EST07 - QUALITY CONTROL & PROFITABILITY CHECKS |  | Not Started | Low |  |  | Job Stage
04. Allowance has been made for material waste and damage, especially for fragile items like finishes, tiles, cladding, and glass. | EST07 - QUALITY CONTROL & PROFITABILITY CHECKS |  | Not Started | Low |  |  | Job Stage
05. Costs for delivery, crane hire, and unloading materials have been included. | EST07 - QUALITY CONTROL & PROFITABILITY CHECKS |  | Not Started | Low |  |  | Job Stage
06. A ‘mistake margin’ has been added to protect against inaccurate supplier quotes. | EST07 - QUALITY CONTROL & PROFITABILITY CHECKS |  | Not Started | Low |  |  | Job Stage
07. Labour hours from past projects have been reviewed and grouped by construction phase and how complex they were. | EST07 - QUALITY CONTROL & PROFITABILITY CHECKS |  | Not Started | Low |  |  | Job Stage
08. Labour time for pre-construction and planning (like design coordination, cost reviews, early contractor involvement meetings, and following up with consultants) has been accounted for. | EST07 - QUALITY CONTROL & PROFITABILITY CHECKS |  | Not Started | Low |  |  | Job Stage
09. Daily time for setting up and packing down on site has been included in labor calculations. | EST07 - QUALITY CONTROL & PROFITABILITY CHECKS |  | Not Started | Low |  |  | Job Stage
10. Project management labour (at least 2 hours per day) has been included. | EST07 - QUALITY CONTROL & PROFITABILITY CHECKS |  | Not Started | Low |  |  | Job Stage
11. Time for team meetings, toolbox talks, and site reviews has been included in labor calculations. | EST07 - QUALITY CONTROL & PROFITABILITY CHECKS |  | Not Started | Low |  |  | Job Stage
12. Productivity losses (due to weather, material delays, late deliveries, site crowding) have been accounted for by adding a 5–10% buffer to tasks. | EST07 - QUALITY CONTROL & PROFITABILITY CHECKS |  | Not Started | Low |  |  | Job Stage
13. Labour for fixing things and correcting defects (at least 1–2% of total labour) has been included. | EST07 - QUALITY CONTROL & PROFITABILITY CHECKS |  | Not Started | Low |  |  | Job Stage
14. Time for learning how to install new products has been allowed. | EST07 - QUALITY CONTROL & PROFITABILITY CHECKS |  | Not Started | Low |  |  | Job Stage
15. Quality assurance and documentation labour (like taking photos, doing inspections, and getting sign-offs) has been planned for. | EST07 - QUALITY CONTROL & PROFITABILITY CHECKS |  | Not Started | Low |  |  | Job Stage
16. Contingency days have been added to the construction timeline, especially for custom or architect-designed homes. | EST07 - QUALITY CONTROL & PROFITABILITY CHECKS |  | Not Started | Low |  |  | Job Stage
17. Square metre rates are not used in the estimate; costs are broken down properly. | EST07 - QUALITY CONTROL & PROFITABILITY CHECKS |  | Not Started | Low |  |  | Job Stage
18. The overhead percentage has been set based on real financial data (e.g., from a 6-month profit and loss report). | EST07 - QUALITY CONTROL & PROFITABILITY CHECKS |  | Not Started | Low |  |  | Job Stage
19. Overhead costs have been applied BEFORE calculating the profit margin. | EST07 - QUALITY CONTROL & PROFITABILITY CHECKS |  | Not Started | Low |  |  | Job Stage
20. A 25–35% mark-up has been targeted depending on the project size and risk. | EST07 - QUALITY CONTROL & PROFITABILITY CHECKS |  | Not Started | Low |  |  | Job Stage
21. The difference between profit margin and mark-up is understood. | EST07 - QUALITY CONTROL & PROFITABILITY CHECKS |  | Not Started | Low |  |  | Job Stage
22. A $3,000–$5,000 allowance for consumables for all builds (this amount depends on the project size) has been included. | EST07 - QUALITY CONTROL & PROFITABILITY CHECKS |  | Not Started | Low |  |  | Job Stage
23. Full insurance coverage (for construction work, public liability, tools, and workers' compensation) has been included. | EST07 - QUALITY CONTROL & PROFITABILITY CHECKS |  | Not Started | Low |  |  | Job Stage
24. An allowance for tool maintenance and depreciation has been included. | EST07 - QUALITY CONTROL & PROFITABILITY CHECKS |  | Not Started | Low |  |  | Job Stage
25. An allowance for site signage, fencing, and administration costs has been included. | EST07 - QUALITY CONTROL & PROFITABILITY CHECKS |  | Not Started | Low |  |  | Job Stage
26. Costs for bin hire, site cleaning, and waste management have been included. | EST07 - QUALITY CONTROL & PROFITABILITY CHECKS |  | Not Started | Low |  |  | Job Stage
27. A 2–4% minimum contingency has been added based on project complexity, document quality, and the team’s risk level. | EST07 - QUALITY CONTROL & PROFITABILITY CHECKS |  | Not Started | Low |  |  | Job Stage
28. A buffer for changes in Provisional Cost (PC) and Provisional Sum (PS) items has been added. | EST07 - QUALITY CONTROL & PROFITABILITY CHECKS |  | Not Started | Low |  |  | Job Stage
29. A $1,000–$2,000 risk allowance for each major subcontractor has been added. | EST07 - QUALITY CONTROL & PROFITABILITY CHECKS |  | Not Started | Low |  |  | Job Stage
30. A 5–10% escalation buffer has been added if the quote is given more than 6 months before construction starts. | EST07 - QUALITY CONTROL & PROFITABILITY CHECKS |  | Not Started | Low |  |  | Job Stage
31. Final Action: I acknowledge that all items on this checklist have been completed. Move to the next phase and load the next checklist. | EST07 - QUALITY CONTROL & PROFITABILITY CHECKS |  | Not Started | Low |  |  | Job Stage
EST08 - TAKE OFF & INTERNAL REVIEW |  |  | Not Started | Low |  |  | Job Stage
01. The Job Folder is set up correctly and files are saved in the right order. | EST08 - TAKE OFF & INTERNAL REVIEW |  | Not Started | Low |  |  | Job Stage
02. The correct documents are being used for the material quantity take-off. | EST08 - TAKE OFF & INTERNAL REVIEW |  | Not Started | Low |  |  | Job Stage
03. The status of questions for clarification (RFIs) and pricing requests (RFQs) has been checked, and any outstanding items have been followed up on. | EST08 - TAKE OFF & INTERNAL REVIEW |  | Not Started | Low |  |  | Job Stage
04. The categories and method used for the material quantity take-off have been checked. | EST08 - TAKE OFF & INTERNAL REVIEW |  | Not Started | Low |  |  | Job Stage
05. Specifications have been double-checked to make sure all items are covered. | EST08 - TAKE OFF & INTERNAL REVIEW |  | Not Started | Low |  |  | Job Stage
06. All labour totals have been triple-checked. | EST08 - TAKE OFF & INTERNAL REVIEW |  | Not Started | Low |  |  | Job Stage
07. The material quantity take-off has been printed out and reviewed. | EST08 - TAKE OFF & INTERNAL REVIEW |  | Not Started | Low |  |  | Job Stage
08. The material quantity take-off has been reviewed with fresh eyes after a break. | EST08 - TAKE OFF & INTERNAL REVIEW |  | Not Started | Low |  |  | Job Stage
09. If the estimate was sent to an external company: Spot-checks or high-level quantity checks have been done on key items from the external company's material quantity take-off. | EST08 - TAKE OFF & INTERNAL REVIEW |  | Not Started | Low |  |  | Job Stage
10. If the estimate was sent to an external company: The external company's material quantity take-off has been compared with your understanding of the plans and specifications. | EST08 - TAKE OFF & INTERNAL REVIEW |  | Not Started | Low |  |  | Job Stage
11. If the estimate was sent to an external company: An internal review of the external company's method and accuracy has been completed. | EST08 - TAKE OFF & INTERNAL REVIEW |  | Not Started | Low |  |  | Job Stage
12. A meeting has been conducted to review the take-offs. | EST08 - TAKE OFF & INTERNAL REVIEW |  | Not Started | Low |  |  | Job Stage
13. This meeting serves as the main quality control point for the take-offs. | EST08 - TAKE OFF & INTERNAL REVIEW |  | Not Started | Low |  |  | Job Stage
14. Final Action: I acknowledge that all items on this checklist have been completed. Move to the next phase and load the next checklist. | EST08 - TAKE OFF & INTERNAL REVIEW |  | Not Started | Low |  |  | Job Stage
EST09 - REVIEW & ALIGNMENT |  |  | Not Started | Low |  |  | Job Stage
01. The completed estimate has been reviewed for accuracy at least 5 times, focusing on different areas (building structure, finishes, services, outside work, and assumptions). | EST09 - REVIEW & ALIGNMENT |  | Not Started | Low |  |  | Job Stage
02. A second experienced estimator has reviewed the proposal. | EST09 - REVIEW & ALIGNMENT |  | Not Started | Low |  |  | Job Stage
03. A thorough cost analysis has been completed. | EST09 - REVIEW & ALIGNMENT |  | Not Started | Low |  |  | Job Stage
04. A risk assessment (at least 2–4% contingency based on how complex the project is, how good the documents are, and the team’s risk level) has been completed. | EST09 - REVIEW & ALIGNMENT |  | Not Started | Low |  |  | Job Stage
05. A preliminary meeting with the client has been held to talk about the estimate and agree on the budget. | EST09 - REVIEW & ALIGNMENT |  | Not Started | Low |  |  | Job Stage
06. The estimate has been finalised. | EST09 - REVIEW & ALIGNMENT |  | Not Started | Low |  |  | Job Stage
07. Internal approval has been obtained: Approval Stage 1. | EST09 - REVIEW & ALIGNMENT |  | Not Started | Low |  |  | Job Stage
08. Internal approval has been obtained: Approval Stage 2. | EST09 - REVIEW & ALIGNMENT |  | Not Started | Low |  |  | Job Stage
09. Internal approval has been obtained: Approval Stage 3. | EST09 - REVIEW & ALIGNMENT |  | Not Started | Low |  |  | Job Stage
10. Profit margin or mark-up has been recalculated after each project to keep improving. | EST09 - REVIEW & ALIGNMENT |  | Not Started | Low |  |  | Job Stage
11. A margin rebalancer has been used if the client questions the profit margin. | EST09 - REVIEW & ALIGNMENT |  | Not Started | Low |  |  | Job Stage
12. Any drawing issues in the estimate (including revision numbers and dates) have been noted. | EST09 - REVIEW & ALIGNMENT |  | Not Started | Low |  |  | Job Stage
13. Final Action: I acknowledge that all items on this checklist have been completed. Move to the next phase and load the next checklist. | EST09 - REVIEW & ALIGNMENT |  | Not Started | Low |  |  | Job Stage
EST10 - FINAL ESTIMATE DOUBLE CHECK |  |  | Not Started | Low |  |  | Job Stage
01. Final checks of the overall estimate have been performed. | EST10 - FINAL ESTIMATE DOUBLE CHECK |  | Not Started | Low |  |  | Job Stage
02. The mark-up or profit margin is correctly applied and checked. | EST10 - FINAL ESTIMATE DOUBLE CHECK |  | Not Started | Low |  |  | Job Stage
03. All labour totals have been cross-checked again. | EST10 - FINAL ESTIMATE DOUBLE CHECK |  | Not Started | Low |  |  | Job Stage
04. Home Warranty details are included. | EST10 - FINAL ESTIMATE DOUBLE CHECK |  | Not Started | Low |  |  | Job Stage
05. The final proposal has been printed and reviewed. | EST10 - FINAL ESTIMATE DOUBLE CHECK |  | Not Started | Low |  |  | Job Stage
06. If the estimate was sent to an external company: The external company's labour totals have been cross-checked against your own benchmarks. | EST10 - FINAL ESTIMATE DOUBLE CHECK |  | Not Started | Low |  |  | Job Stage
07. If the estimate was sent to an external company: All required allowances and buffers (for waste, consumables, project management labour, lost productivity) have been confirmed as correctly applied by the external estimator. | EST10 - FINAL ESTIMATE DOUBLE CHECK |  | Not Started | Low |  |  | Job Stage
08. If the estimate was sent to an external company: All insurance, tool maintenance, and site allowances from your standards have been confirmed as included in the external estimate. | EST10 - FINAL ESTIMATE DOUBLE CHECK |  | Not Started | Low |  |  | Job Stage
09. Final Action: I acknowledge that all items on this checklist have been completed. Move to the next phase and load the next checklist. | EST10 - FINAL ESTIMATE DOUBLE CHECK |  | Not Started | Low |  |  | Job Stage
EST11 - VALUE MANAGEMENT REVIEW |  |  | Not Started | Low |  |  | Job Stage
01. Specific project areas have been identified for value management review. | EST11 - VALUE MANAGEMENT REVIEW |  | Not Started | Low |  |  | Job Stage
02. Potential cost-saving alternatives for identified areas have been explored. | EST11 - VALUE MANAGEMENT REVIEW |  | Not Started | Low |  |  | Job Stage
03. Impact of value management changes on quality and functionality has been assessed. | EST11 - VALUE MANAGEMENT REVIEW |  | Not Started | Low |  |  | Job Stage
04. Value management options have been presented for review. | EST11 - VALUE MANAGEMENT REVIEW |  | Not Started | Low |  |  | Job Stage
05. Decisions on value management changes have been recorded. | EST11 - VALUE MANAGEMENT REVIEW |  | Not Started | Low |  |  | Job Stage
06. Final Action: I acknowledge that all items on this checklist have been completed. Move to the next phase and load the next checklist. | EST11 - VALUE MANAGEMENT REVIEW |  | Not Started | Low |  |  | Job Stage
EST12 - ESTIMATE DELIVERY |  |  | Not Started | Low |  |  | Job Stage
01. A pricing presentation (using visuals, quantities, and charts) has been created. | EST12 - ESTIMATE DELIVERY |  | Not Started | Low |  |  | Job Stage
02. Clients have been walked through the estimate in person. | EST12 - ESTIMATE DELIVERY |  | Not Started | Low |  |  | Job Stage
03. All verbal changes have been written down and attached to the estimate. | EST12 - ESTIMATE DELIVERY |  | Not Started | Low |  |  | Job Stage
04. The review meeting has been conducted. | EST12 - ESTIMATE DELIVERY |  | Not Started | Low |  |  | Job Stage
05. Final Action: I acknowledge that all items on this checklist have been completed. Move to the next phase and load the next checklist. | EST12 - ESTIMATE DELIVERY |  | Not Started | Low |  |  | Job Stage
EST13 - OFFER & SUBMISSION |  |  | Not Started | Low |  |  | Job Stage
01. The Letter of Offer, including all terms and conditions, has been prepared. | EST13 - OFFER & SUBMISSION |  | Not Started | Low |  |  | Job Stage
02. The Letter of Offer has been reviewed for accuracy and completeness. | EST13 - OFFER & SUBMISSION |  | Not Started | Low |  |  | Job Stage
03. Summary pages and detailed breakdowns are included in the offer. | EST13 - OFFER & SUBMISSION |  | Not Started | Low |  |  | Job Stage
04. Prime Cost (PC) and Provisional Sum (PS) allowances are clearly labeled and use realistic values. | EST13 - OFFER & SUBMISSION |  | Not Started | Low |  |  | Job Stage
05. A scope of works is included with every estimate, clearly stating what is included and what is not. | EST13 - OFFER & SUBMISSION |  | Not Started | Low |  |  | Job Stage
06. A Rock Clause (allowing for rock removal at a cost per cubic meter or as a Provisional Sum) is included. | EST13 - OFFER & SUBMISSION |  | Not Started | Low |  |  | Job Stage
07. A Connection Clause (stating all service fees and connection costs are covered by the client unless otherwise noted) is included. | EST13 - OFFER & SUBMISSION |  | Not Started | Low |  |  | Job Stage
08. A Weather Delay Clause (including specific allowances for rain days and terms for extending time) is included. | EST13 - OFFER & SUBMISSION |  | Not Started | Low |  |  | Job Stage
09. A Material Escalation Clause (to protect the business against supplier price increases after the contract is signed) is included. | EST13 - OFFER & SUBMISSION |  | Not Started | Low |  |  | Job Stage
10. A Provisional Cost Item Selection Deadline Clause (to prevent delays caused by clients who take too long to make selections) is included. | EST13 - OFFER & SUBMISSION |  | Not Started | Low |  |  | Job Stage
11. An Exclusions Clause (clearly listing what has NOT been priced) is included. | EST13 - OFFER & SUBMISSION |  | Not Started | Low |  |  | Job Stage
12. A Handover & Defects Clause (explaining how long defects will be attended to and what is excluded) is included. | EST13 - OFFER & SUBMISSION |  | Not Started | Low |  |  | Job Stage
12. The Letter of Offer has been submitted to the client. | EST13 - OFFER & SUBMISSION |  | Not Started | Low |  |  | Job Stage
13. The client has been followed up with to answer any questions and address any concerns. | EST13 - OFFER & SUBMISSION |  | Not Started | Low |  |  | Job Stage
14. All contract documents have been prepared and sent to the client for review. | EST13 - OFFER & SUBMISSION |  | Not Started | Low |  |  | Job Stage
15. Meeting minutes have been created and followed up on. | EST13 - OFFER & SUBMISSION |  | Not Started | Low |  |  | Job Stage
16. Final Action: I acknowledge that all items on this checklist have been completed. Move to the next phase and load the next checklist. | EST13 - OFFER & SUBMISSION |  | Not Started | Low |  |  | Job Stage
EST14 - ACCEPTED |  |  | Not Started | Low |  |  | Job Stage
01. Client acceptance of the Letter of Offer has been confirmed. | EST14 - ACCEPTED |  | Not Started | Low |  |  | Job Stage
02. The construction team has been onboarded. | EST14 - ACCEPTED |  | Not Started | Low |  |  | Job Stage
03. The project file has been transferred to the operations team. | EST14 - ACCEPTED |  | Not Started | Low |  |  | Job Stage
04. All relevant documents have been updated and loaded into the project management system. | EST14 - ACCEPTED |  | Not Started | Low |  |  | Job Stage
05. The construction job has been created in the project management system. | EST14 - ACCEPTED |  | Not Started | Low |  |  | Job Stage
06. Final Action: I acknowledge that all items on this checklist have been completed. | EST14 - ACCEPTED |  | Not Started | Low |  |  | Job Stage
EST15 - LOST ESTIMATE ACTIONS |  |  | Not Started | Low |  |  | Job Stage
01. The reason for the estimate being lost or not accepted has been identified and recorded. | EST15 - LOST ESTIMATE ACTIONS |  | Not Started | Low |  |  | Job Stage
02. Feedback from the client (if available) has been collected and documented. | EST15 - LOST ESTIMATE ACTIONS |  | Not Started | Low |  |  | Job Stage
03. Lessons learned from the lost estimate have been identified and reviewed internally. | EST15 - LOST ESTIMATE ACTIONS |  | Not Started | Low |  |  | Job Stage
04. Any necessary adjustments to the estimating process or sales strategy have been documented. | EST15 - LOST ESTIMATE ACTIONS |  | Not Started | Low |  |  | Job Stage
05. The project status has been updated to "Lost" in the project management system. | EST15 - LOST ESTIMATE ACTIONS |  | Not Started | Low |  |  | Job Stage
06. Final Action: I acknowledge that all items on this checklist have been completed. | EST15 - LOST ESTIMATE ACTIONS |  | Not Started | Low |  |  | Job Stage